## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| RO | 1376 | Error deleting port: PortNotFoundClient | Master | IN_PROGRESS | david.garcia@canonical.com | gulsum.atici@canonical.com | 2020-12-16 11:38 | CURRENT | 2022-03-28 01:12 | CURRENT | 2022-03-11 11:50 | bug_status | 2022-03-28 01:12 | CURRENT | 4 | 1 |  |  | 2

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1123 | NS Instantiate nsName as required property [sol005robot] | Master | OPEN-UNCONFIRMED | frank.bryden@etsi.org | gerardo.garciadeblas@telefonica.com | 2020-07-06 15:05 | CURRENT | 2020-07-06 15:05 | CURRENT | 2022-03-22 16:31 | version | 2022-03-22 16:31 | CURRENT | 1 | 0 | 1 |  | 3
| IM-NBI | 1188 | Uploading NSD content of NSD in state 'ONBOARDED' [sol005robot] | Master | IN_PROGRESS | frank.bryden@etsi.org | gerardo.garciadeblas@telefonica.com | 2020-08-10 16:34 | CURRENT | 2020-08-14 09:00 | CURRENT | 2022-03-22 16:34 | comment | 2022-04-05 17:11 | CURRENT | 2 | 0 | 1 |  | 4
| IM-NBI | 1266 | Error on using object type parameter for actions from OSM | Master | CONFIRMED | preethika.p@tataelxsi.co.in | jmguzman@whitestack.com | 2020-10-19 06:41 | CURRENT | 2021-12-10 10:21 | CURRENT | 2021-12-10 10:21 | version | 2021-12-10 10:21 | CURRENT | 2 | 0 | 1 | 1 | 1
| OSMClient | 1428 | k8scluster-update command does not work | v9.0 | OPEN-UNCONFIRMED | alimonj@indra.es | mark.beierl@canonical.com | 2021-02-02 11:54 | CURRENT | 2021-02-02 11:54 | CURRENT | 2021-11-29 16:34 | component | 2021-11-29 16:34 | CURRENT | 1 | 0 |  | 1 | 1
| LCM | 1443 | No info about the VDUs in VDU_SCALE_INFO parameter in scaling config actions | v9.0 | OPEN-UNCONFIRMED | alimonj@indra.es | glavado@whitestack.com | 2021-02-18 10:06 | CURRENT | 2021-02-18 10:06 | CURRENT | 2022-02-16 15:38 | cc | 2022-02-16 15:38 | CURRENT | 1 | 0 |  |  | 1
| IM-NBI | 1454 | OSM Performance Report missing Object descriptorType | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com | agarcia@whitestack.com | 2021-02-25 17:49 | CURRENT | 2021-02-25 17:49 | CURRENT | 2021-07-08 17:41 | comment | 2021-11-29 16:28 | CURRENT | 1 | 0 |  |  | 2
| Robot-tests | 1546 | Missing E2E test for subscription API client | Master | OPEN-UNCONFIRMED | daguilarh@indra.es |  | 2021-05-27 11:36 | CURRENT | 2021-05-27 11:36 | CURRENT |  | cc | 2021-05-27 11:38 | CURRENT | 1 | 0
| N2VC | 1551 | All LXD proxy charms use the same series | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-05-28 12:32 | CURRENT | 2021-05-28 12:32 | CURRENT |  | comment | 2021-05-31 19:58 | CURRENT | 1 | 0
| DEVOPS | 1562 | Not possible to set log level for the modules during installation | v10.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-06-03 18:31 | CURRENT | 2021-06-03 18:31 | CURRENT |  | comment | 2021-09-02 12:03 | CURRENT | 1 | 0
| DEVOPS | 1563 | Stage3 does not archive containers logs when OSM is not healthy | v10.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-06-03 18:36 | CURRENT | 2021-06-03 18:36 | CURRENT |  | comment | 2022-04-08 16:39 | CURRENT | 1 | 0
| LCM | 1579 | Error read ns record from database when execute action in function _on_update_n2vc_db | Master | OPEN-UNCONFIRMED | cuongbo97@gmail.com | glavado@whitestack.com | 2021-06-21 12:52 | CURRENT | 2021-06-21 12:52 | CURRENT | 2022-02-16 15:40 | cc | 2022-02-16 15:40 | CURRENT | 1 | 0 |  |  | 1
| N2VC | 1584 | Failure updating the ns state with distributed VCA | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-06-22 11:27 | CURRENT | 2021-06-22 11:27 | CURRENT |  | comment | 2021-06-22 11:27 | CURRENT | 1 | 0
| RO | 1603 | Dummy VIM fails in HA configuration | v10.0 | IN_PROGRESS | mark.beierl@canonical.com | gulsum.atici@canonical.com | 2021-07-23 16:10 | CURRENT | 2022-03-28 01:13 | CURRENT | 2022-03-15 13:42 | bug_status | 2022-03-28 01:13 | CURRENT | 2 | 0 |  |  | 2
| RO | 1607 | the interface position is not taken into account | v10.0 | IN_PROGRESS | endika.aldecoa@ehu.eus | gulsum.atici@canonical.com | 2021-07-26 16:55 | CURRENT | 2022-03-28 01:21 | CURRENT | 2022-03-15 13:42 | bug_status | 2022-03-28 01:21 | CURRENT | 2 | 0 |  |  | 2
| LCM | 1621 | Execution enviroment not being created at initial deployment | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr | emin.aktas@ulakhaberlesme.com.tr | 2021-07-30 16:03 | CURRENT | 2021-07-30 16:03 | CURRENT | 2021-08-04 10:45 | comment | 2021-09-09 08:56 | CURRENT | 1 | 0 |  |  | 1
| IM-NBI | 1622 | Status report not consistent between NS and VNF | v10.0 | OPEN-UNCONFIRMED | guillermo.gomez.external@atos.net | gerardo.garciadeblas@telefonica.com | 2021-08-02 10:41 | CURRENT | 2021-08-02 10:41 | CURRENT | 2022-03-28 17:20 | component | 2022-03-28 17:20 | CURRENT | 1 | 0 |  | 1 | 1
| N2VC | 1623 | Lost connection: Error registering native charm | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-03 16:39 | CURRENT | 2021-08-03 16:39 | CURRENT |  | comment | 2021-08-03 16:39 | CURRENT | 1 | 0
| N2VC | 1631 | Cannot add instantiation parameters for Juju bundles (KNF) | v10.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:51 | CURRENT | 2021-08-09 16:51 | CURRENT |  | comment | 2021-08-09 16:51 | CURRENT | 1 | 0
| RO | 1640 | Error at create vdu: 'NoneType' object does not support item assignment | Master | IN_PROGRESS | e.dah.tid@telefonica.com | gulsum.atici@canonical.com | 2021-08-24 14:08 | CURRENT | 2022-03-28 01:14 | CURRENT | 2022-03-15 13:41 | bug_status | 2022-03-28 01:14 | CURRENT | 2 | 0 |  |  | 2
| LCM | 1646 | Error when performing scale_out of an instance using execution environment | v10.0 | OPEN-UNCONFIRMED | paula.encinar@atos.net | glavado@whitestack.com | 2021-08-26 15:26 | CURRENT | 2021-08-26 15:26 | CURRENT | 2022-02-16 15:37 | cc | 2022-02-16 15:37 | CURRENT | 1 | 0 |  |  | 1
| LCM | 1730 | LCM does not delete Helm based NS properly | v10.0 | OPEN-UNCONFIRMED | mark.beierl@canonical.com | glavado@whitestack.com | 2021-11-04 20:19 | CURRENT | 2021-11-04 20:19 | CURRENT | 2022-02-16 15:38 | cc | 2022-02-16 15:38 | CURRENT | 1 | 0 |  |  | 1
| IM-NBI | 1752 | NBI does not validate manifest hashes from SOL004/SOL007 packages | v11.0 | OPEN-UNCONFIRMED | fbravo@whitestack.com | glavado@whitestack.com | 2021-11-10 15:33 | CURRENT | 2021-11-10 15:33 | CURRENT | 2022-02-16 15:41 | assigned_to | 2022-02-16 15:41 | CURRENT | 1 | 0 |  |  | 2
| RO | 1769 | GCP connector doesn't provide internet access for management network | v11.0 | CONFIRMED | sgallardor@indra.es | sgallardor@indra.es | 2021-11-15 11:53 | CURRENT | 2021-12-13 11:54 | CURRENT | 2021-11-15 12:48 | everconfirmed | 2021-12-13 11:54 | CURRENT | 2 | 0 |  |  | 1
| IM-NBI | 1808 | Validation in the NBI does not check mandatory fields | v11.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com | jmguzman@whitestack.com | 2021-11-29 16:39 | CURRENT | 2021-11-29 16:39 | CURRENT | 2021-11-29 16:39 | cc | 2021-11-29 16:41 | CURRENT | 1 | 0 |  |  | 1
| N2VC | 1815 | OSM can't fetch changes after helm repository update | v10.0 | CONFIRMED | starazona@whitestack.com | david.garcia@canonical.com | 2021-12-01 18:05 | CURRENT | 2022-04-06 15:35 | CURRENT | 2022-04-09 00:06 | comment | 2022-04-18 17:09 | CURRENT | 2 | 0 |  | 1 | 2
| MON | 1817 | MON is monitoring deleted network service | v11.0 | OPEN-UNCONFIRMED | subhankar.pal@altran.com |  | 2021-12-03 06:10 | CURRENT | 2021-12-03 06:10 | CURRENT |  | comment | 2021-12-03 06:10 | CURRENT | 1 | 0
| N2VC | 1824 | Error when deleting k8s charm NS instance | v11.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2021-12-10 10:59 | CURRENT | 2021-12-10 10:59 | CURRENT |  | cc | 2021-12-10 10:59 | CURRENT | 1 | 0
| IM-NBI | 1825 | Create subscription problem | v10.0 | OPEN-UNCONFIRMED | tolga.golelcin@telenity.com |  | 2021-12-13 11:09 | CURRENT | 2021-12-13 11:09 | CURRENT |  | comment | 2021-12-13 11:10 | CURRENT | 1 | 0
| N2VC | 1828 | KNF instantiation fails when relying on untrusted Helm chart repo | v11.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com | gerardo.garciadeblas@telefonica.com | 2021-12-13 12:10 | CURRENT | 2021-12-13 12:10 | CURRENT | 2021-12-13 15:17 | assigned_to | 2021-12-13 15:17 | CURRENT | 1 | 0 |  |  | 1
| OSMClient | 1862 | OSM Repositories not working for OSM v11.0 | v11.0 | OPEN-UNCONFIRMED | jgfierro@indra.es |  | 2022-01-18 13:24 | CURRENT | 2022-01-18 13:24 | CURRENT |  | comment | 2022-01-18 13:24 | CURRENT | 1 | 0
| LCM | 1887 | Exception when trying to create execution environment | v11.0 | OPEN-UNCONFIRMED | paranda@it.uc3m.es |  | 2022-03-01 07:48 | CURRENT | 2022-03-01 07:48 | CURRENT |  | comment | 2022-03-03 10:45 | CURRENT | 1 | 0
| LCM | 1921 | Helm EE has security risks | master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-03-21 20:13 | CURRENT | 2022-03-21 20:13 | CURRENT |  | cc | 2022-03-21 20:16 | CURRENT | 1 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| PLA | 1213 | vnf_price_list.yaml with prices per project contains an unnecessary sequence collection in the yaml file | v8.0 | OPEN-UNCONFIRMED | lars-goran.magnusson@arctoslabs.com |  | 2020-09-17 09:28 | CURRENT | 2020-09-17 09:28 | CURRENT |  | comment | 2020-09-17 09:28 | CURRENT | 1 | 0
| N2VC | 1234 | OSM reports successful deployment when a charm relation fails | v8.0 | OPEN-UNCONFIRMED | endika.aldecoa@ehu.eus |  | 2020-09-25 12:29 | CURRENT | 2020-09-25 12:29 | CURRENT |  | comment | 2021-12-16 15:22 | CURRENT | 1 | 0
| Bugzilla | 1269 | Clean up of old bugs | unspecified | IN_PROGRESS | silvia.almagia@etsi.org |  | 2020-10-20 17:13 | CURRENT | 2022-04-08 14:17 | CURRENT |  | bug_status | 2022-04-08 14:17 | CURRENT | 7 | 1
| IM-NBI | 1301 | Hardcoded credentials in code | v8.0 | OPEN-UNCONFIRMED | javier.ramon@telefonica.com | mark.beierl@canonical.com | 2020-11-27 15:55 | CURRENT | 2020-11-27 15:55 | CURRENT | 2021-10-26 16:44 | target_milestone | 2021-10-26 16:44 | CURRENT | 1 | 0 |  | 1 | 1
| IM-NBI | 1305 | Remove self-signed SSL certificate from NBI | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | mark.beierl@canonical.com | 2020-12-01 19:19 | CURRENT | 2020-12-01 19:19 | CURRENT | 2021-10-26 16:44 | cc | 2021-10-26 16:44 | CURRENT | 1 | 0 |  | 1 | 1
| NG-UI | 1346 | NG-UI: cookie-0.3.1 / cookie-0.4.0 | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | barath.r@tataelxsi.co.in | 2020-12-03 01:37 | CURRENT | 2020-12-03 01:37 | CURRENT | 2021-08-10 17:17 | component | 2021-08-10 17:17 | CURRENT | 1 | 0 |  | 1 | 1
| NG-UI | 1347 | NG-UI: faye-websocket-0.10.0 | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | barath.r@tataelxsi.co.in | 2020-12-03 01:38 | CURRENT | 2020-12-03 01:38 | CURRENT | 2021-08-10 17:17 | component | 2021-08-10 17:17 | CURRENT | 1 | 0 |  | 1 | 1
| NG-UI | 1348 | NG-UI: npm-user-validate-1.0.0 | v9.0 | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | barath.r@tataelxsi.co.in | 2020-12-03 01:39 | CURRENT | 2020-12-03 01:39 | CURRENT | 2021-08-10 17:17 | component | 2021-08-10 17:17 | CURRENT | 1 | 0 |  | 1 | 1
| DEVOPS | 1366 | 413 Error - Entity Too Large | v8.0 | OPEN-UNCONFIRMED | ragavi.d@tataelxsi.co.in |  | 2020-12-09 09:02 | CURRENT | 2020-12-09 09:02 | CURRENT |  | comment | 2020-12-09 09:02 | CURRENT | 1 | 0
| NG-UI | 1420 | UI composes new VNF/NS package not in SOL006 format | v9.0 | OPEN-UNCONFIRMED | alexander.onnikov@xored.com | ramerama@tataelxsi.co.in | 2021-01-27 07:35 | CURRENT | 2021-01-27 07:35 | CURRENT | 2022-02-16 15:43 | assigned_to | 2022-02-16 15:43 | CURRENT | 1 | 0 |  | 2 | 3
| DEVOPS | 1451 | High memory consumption in MongoDB process | v9.0 | CONFIRMED | daguilarh@indra.es | mark.beierl@canonical.com | 2021-02-25 13:05 | CURRENT | 2021-02-25 13:43 | CURRENT | 2021-02-25 13:43 | comment | 2021-12-21 11:06 | CURRENT | 2 | 0 |  | 1 | 1
| LCM | 1487 | Group coordinator failure issue is coming in between LCM and KAFKA often | v8.0 | CONFIRMED | vijay.r@tataelxsi.co.in | glavado@whitestack.com | 2021-03-29 16:47 | CURRENT | 2021-07-20 00:16 | CURRENT | 2022-02-16 15:37 | cc | 2022-02-16 15:37 | CURRENT | 2 | 0 |  |  | 1
| OSMClient | 1519 | osm package-translate not working for descriptors containing EE config | v9.0 | OPEN-UNCONFIRMED | paula.encinar@atos.net |  | 2021-04-28 16:39 | CURRENT | 2021-04-28 16:39 | CURRENT |  | comment | 2021-04-28 16:39 | CURRENT | 1 | 0
| LCM | 1534 | EE pods are not decomissioned along with VNF | v9.0 | CONFIRMED | guillermo.gomez.external@atos.net | glavado@whitestack.com | 2021-05-12 15:19 | CURRENT | 2021-05-12 22:01 | CURRENT | 2022-02-16 15:37 | cc | 2022-02-16 15:37 | CURRENT | 2 | 0 |  | 2 | 3
| IM-NBI | 1557 | Multiple VNFs using same VNFD ID at NSD can't connect to different networks | Master | OPEN-UNCONFIRMED | glavado@whitestack.com | glavado@whitestack.com | 2021-06-03 17:23 | CURRENT | 2021-06-03 17:23 | CURRENT | 2022-02-16 15:40 | assigned_to | 2022-02-16 15:40 | CURRENT | 1 | 0 |  |  | 2
| common | 1577 | NF/NS packages are not removed from LCM when the NS or NF is deleted | v9.0 | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com | mark.beierl@canonical.com | 2021-06-18 17:02 | CURRENT | 2021-06-18 17:02 | CURRENT | 2022-02-16 15:46 | cc | 2022-02-16 15:46 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1581 | Full_instas.sh do not remove osm-ım and osm-devops | v10.0 | OPEN-UNCONFIRMED | mehmet.basar@ulakhaberlesme.com.tr |  | 2021-06-21 13:42 | CURRENT | 2021-06-21 13:42 | CURRENT |  | comment | 2021-06-21 13:42 | CURRENT | 1 | 0
| OSMClient | 1611 | Error deleting VNFD by name | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | glavado@whitestack.com | 2021-07-29 10:56 | CURRENT | 2021-07-29 10:56 | CURRENT | 2022-02-16 15:40 | cc | 2022-02-16 15:40 | CURRENT | 1 | 0 |  |  | 2
| LCM | 1629 | OSMLCM_VCA_ENABLEOSUPGRADE not working | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr | glavado@whitestack.com | 2021-08-06 16:14 | CURRENT | 2021-08-06 16:14 | CURRENT | 2022-02-16 15:41 | cc | 2022-02-16 15:41 | CURRENT | 1 | 0 |  |  | 1
| N2VC | 1630 | Cannot add instantiation parameters for Juju bundles (KNF) | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:50 | CURRENT | 2021-08-09 16:50 | CURRENT |  | comment | 2021-08-09 16:51 | CURRENT | 1 | 0
| N2VC | 1632 | Cannot add instantiation parameters for Juju bundles (KNF) | v9.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:52 | CURRENT | 2021-08-09 16:52 | CURRENT |  | comment | 2021-08-09 16:52 | CURRENT | 1 | 0
| RO | 1644 | 'Error at create vdu: unknown' when instantiating network slice | v10.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com | gulsum.atici@canonical.com | 2021-08-26 14:57 | CURRENT | 2021-08-26 14:57 | CURRENT | 2022-03-15 13:41 | assigned_to | 2022-03-15 13:41 | CURRENT | 1 | 0 |  |  | 2
| RO | 1645 | 'Error at create vdu: unknown' when instantiating network slice | v9.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com | gulsum.atici@canonical.com | 2021-08-26 15:03 | CURRENT | 2021-08-26 15:03 | CURRENT | 2022-03-15 13:41 | assigned_to | 2022-03-15 13:41 | CURRENT | 1 | 0 |  |  | 2
| RO | 1649 | 'Error at create vdu: unknown' when instantiating network slice | Master | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com | gulsum.atici@canonical.com | 2021-09-02 10:49 | CURRENT | 2021-09-02 10:49 | CURRENT | 2022-03-15 13:41 | assigned_to | 2022-03-15 13:41 | CURRENT | 1 | 0 |  |  | 2
| IM-NBI | 1660 | PATCH of /ns_descriptors/{nsdInfoId} returns wrong HTTP code[sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-14 17:26 | CURRENT | 2021-09-14 17:26 | CURRENT |  | comment | 2021-09-14 17:26 | CURRENT | 1 | 0
| IM-NBI | 1661 | _id vs id [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-14 17:30 | CURRENT | 2021-09-14 17:30 | CURRENT |  | comment | 2021-09-14 17:30 | CURRENT | 1 | 0
| DEVOPS | 1662 | Controller OSM not found; Unix Socket Permission Denied | v10.0 | OPEN-UNCONFIRMED | tayloreisman2012@gmail.com | mark.beierl@canonical.com | 2021-09-15 01:07 | CURRENT | 2021-09-15 01:07 | CURRENT | 2021-09-15 02:04 | comment | 2021-09-16 16:51 | CURRENT | 1 | 0 |  | 1 | 1
| IM-NBI | 1667 | PATCH of Individual Package should return 200 [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-16 17:09 | CURRENT | 2021-09-16 17:09 | CURRENT |  | comment | 2021-09-16 17:09 | CURRENT | 1 | 0
| IM-NBI | 1668 | VNFPkgInfo contains more fields than required by default [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-16 17:10 | CURRENT | 2021-09-16 17:10 | CURRENT |  | comment | 2021-09-16 17:10 | CURRENT | 1 | 0
| IM-NBI | 1671 | Absence of id [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:51 | CURRENT | 2021-09-20 21:51 | CURRENT |  | comment | 2021-09-20 21:51 | CURRENT | 1 | 0
| IM-NBI | 1672 | Returned data on NsInstance creation does not conform [sol005robot] | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:52 | CURRENT | 2021-09-20 21:52 | CURRENT |  | comment | 2021-09-20 21:52 | CURRENT | 1 | 0
| IM-NBI | 1673 | Launching multiple NS instances with single on-boarded NSD/VNFD just by varying values of IM's fields at NS instantiation time | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:53 | CURRENT | 2021-09-20 21:53 | CURRENT |  | comment | 2021-09-20 21:53 | CURRENT | 1 | 0
| DEVOPS | 1702 | NG-UI container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:39 | CURRENT | 2021-10-14 20:39 | CURRENT | 2021-10-14 20:52 | assigned_to | 2021-10-14 20:52 | CURRENT | 1 | 0 |  | 1 | 2
| DEVOPS | 1704 | LCM container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:41 | CURRENT | 2021-10-14 20:41 | CURRENT | 2021-10-14 20:52 | assigned_to | 2021-10-14 20:52 | CURRENT | 1 | 0 |  | 1 | 2
| DEVOPS | 1708 | PLA container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:44 | CURRENT | 2021-10-14 20:44 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  | 1 | 2
| DEVOPS | 1709 | Keystone container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:45 | CURRENT | 2021-10-14 20:45 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1710 | Zookeeper container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1711 | Kafka container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:46 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1712 | MongoDB container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:47 | CURRENT | 2021-10-14 20:47 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1713 | MySQL container runs as root | unspecified | OPEN-UNCONFIRMED | eduardo.sousa@canonical.com | eduardo.sousa@canonical.com | 2021-10-14 20:48 | CURRENT | 2021-10-14 20:48 | CURRENT | 2021-10-14 20:53 | assigned_to | 2021-10-14 20:53 | CURRENT | 1 | 0 |  |  | 1
| DEVOPS | 1714 | Hangs on 'Waiting for storageClass' | v10.0 | OPEN-UNCONFIRMED | tayloreisman2012@gmail.com |  | 2021-10-15 18:47 | CURRENT | 2021-10-15 18:47 | CURRENT |  | comment | 2021-11-04 15:53 | CURRENT | 1 | 0
| DEVOPS | 1737 | Cleanup of unused options in the community installer | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-11-05 17:32 | CURRENT | 2021-11-05 17:32 | CURRENT |  | comment | 2021-11-25 09:43 | CURRENT | 1 | 0
| DEVOPS | 1738 | Cleanup of unused options in the community installer | v11.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-11-05 17:32 | CURRENT | 2021-11-05 17:32 | CURRENT |  | comment | 2021-11-05 17:32 | CURRENT | 1 | 0
| DEVOPS | 1739 | Cleanup of community installer | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-11-05 17:55 | CURRENT | 2021-11-05 17:55 | CURRENT |  | blocked | 2021-11-05 17:56 | CURRENT | 1 | 0
| DEVOPS | 1740 | Cleanup of community installer | v11.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-11-05 17:56 | CURRENT | 2021-11-05 17:56 | CURRENT |  | comment | 2021-11-05 17:56 | CURRENT | 1 | 0
| RO | 1768 | GCP connector doesn't provide internet access for management network | Master | CONFIRMED | sgallardor@indra.es | sgallardor@indra.es | 2021-11-15 11:47 | CURRENT | 2021-12-13 11:54 | CURRENT | 2021-11-15 11:51 | everconfirmed | 2021-12-13 11:54 | CURRENT | 2 | 0 |  |  | 1
| Robot-tests | 1771 | Get Metric Keyword does not support prometheus authentication | v11.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-11-15 15:54 | CURRENT | 2021-11-15 15:54 | CURRENT |  | comment | 2021-11-15 15:54 | CURRENT | 1 | 0
| Robot-tests | 1772 | Get Metric Keyword does not support prometheus authentication | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2021-11-15 15:54 | CURRENT | 2021-11-15 15:54 | CURRENT |  | comment | 2021-11-15 15:54 | CURRENT | 1 | 0
| DEVOPS | 1790 | K8s installer can go into infinite loop | v11.0 | OPEN-UNCONFIRMED | mark.beierl@canonical.com | gerardo.garciadeblas@telefonica.com | 2021-11-17 16:12 | CURRENT | 2021-11-17 16:12 | CURRENT | 2021-11-18 12:57 | comment | 2021-11-18 14:22 | CURRENT | 1 | 0 | 1 |  | 1
| DEVOPS | 1792 | K8s installer can go into infinite loop | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com | gerardo.garciadeblas@telefonica.com | 2021-11-18 12:54 | CURRENT | 2021-11-18 12:54 | CURRENT | 2021-11-18 12:58 | assigned_to | 2021-11-18 12:58 | CURRENT | 1 | 0 |  |  | 1
| RO | 1820 | Network creation error when instantiating SR-IOV network service | Master | CONFIRMED | e.dah.tid@telefonica.com | gulsum.atici@canonical.com | 2021-12-07 11:21 | CURRENT | 2021-12-15 10:50 | CURRENT | 2022-03-15 13:00 | assigned_to | 2022-03-15 13:00 | CURRENT | 3 | 1 |  |  | 2
| common | 1822 | Use mongodb client with asyncio support | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | mark.beierl@canonical.com | 2021-12-10 10:48 | CURRENT | 2021-12-10 10:48 | CURRENT | 2022-02-16 15:48 | cc | 2022-02-16 15:48 | CURRENT | 1 | 0 |  |  | 1
| common | 1823 | Use mongodb client with asyncio support | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | mark.beierl@canonical.com | 2021-12-10 10:49 | CURRENT | 2021-12-10 10:49 | CURRENT | 2022-02-16 15:49 | cc | 2022-02-16 15:49 | CURRENT | 1 | 0 |  |  | 1
| N2VC | 1826 | KNF instantiation fails when relying on untrusted Helm chart repo | Master | CONFIRMED | e.dah.tid@telefonica.com | gerardo.garciadeblas@telefonica.com | 2021-12-13 12:09 | CURRENT | 2022-03-08 03:58 | CURRENT | 2021-12-13 15:16 | comment | 2022-04-04 20:21 | CURRENT | 3 | 1 |  |  | 1
| N2VC | 1827 | KNF instantiation fails when relying on untrusted Helm chart repo | v10.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com | gerardo.garciadeblas@telefonica.com | 2021-12-13 12:09 | CURRENT | 2021-12-13 12:09 | CURRENT | 2021-12-13 15:17 | assigned_to | 2021-12-13 15:17 | CURRENT | 1 | 0 |  |  | 1
| IM-NBI | 1829 | Missing "NsIdentifierDeletionNotification" notification [SOL005 V3.5.1] | v10.0 | OPEN-UNCONFIRMED | rajeswari.kolluri@oracle.com |  | 2021-12-15 05:51 | CURRENT | 2021-12-15 05:51 | CURRENT |  | comment | 2021-12-15 05:51 | CURRENT | 1 | 0
| LCM | 1830 | Missing "NsLcmOperationOccurrenceNotification(COMPLETED)" notification [SOL005] | v10.0 | OPEN-UNCONFIRMED | rajeswari.kolluri@oracle.com | glavado@whitestack.com | 2021-12-15 06:08 | CURRENT | 2021-12-15 06:08 | CURRENT | 2022-03-15 16:36 | cc | 2022-03-15 16:36 | CURRENT | 1 | 0 |  | 1 | 1
| IM-NBI | 1831 | OSM does not support few operations in NS instances and NS LCM | v11.0 | OPEN-UNCONFIRMED | diksha.trehan@oracle.com |  | 2021-12-15 09:35 | CURRENT | 2021-12-15 09:35 | CURRENT |  | version | 2022-04-20 10:28 | CURRENT | 1 | 0 | 1
| N2VC | 1834 | OSM does not allow to add credential base helm-chart repositories | v10.0 | OPEN-UNCONFIRMED | garomero@indra.es |  | 2021-12-17 09:29 | CURRENT | 2021-12-17 09:29 | CURRENT |  | comment | 2022-01-13 13:03 | CURRENT | 1 | 0
| DEVOPS | 1836 | Error creating machine on juju during ns instantiation while creating execution environment | v11.0 | OPEN-UNCONFIRMED | dominiktopyla@gmail.com |  | 2021-12-22 00:12 | CURRENT | 2021-12-22 00:12 | CURRENT |  | comment | 2022-01-05 14:35 | CURRENT | 1 | 0
| RO | 1851 | Invalid filter 'name' in function 'get_all_vpcs()' in AWS | v11.0 | IN_PROGRESS | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 11:33 | CURRENT | 2022-03-28 01:10 | CURRENT | 2022-03-15 13:00 | bug_status | 2022-03-28 01:10 | CURRENT | 3 | 0 |  |  | 2
| RO | 1852 | AWS VPC subnet not being created when adding virtual-link-profile with IPv4 CIDR | v11.0 | IN_PROGRESS | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 11:54 | CURRENT | 2022-03-28 01:11 | CURRENT | 2022-03-15 13:00 | bug_status | 2022-03-28 01:11 | CURRENT | 3 | 0 |  |  | 2
| RO | 1853 | Error trying to choose disk size for a new VDU in AWS | v11.0 | OPEN-UNCONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:12 | CURRENT | 2022-01-10 14:12 | CURRENT | 2022-03-15 13:00 | assigned_to | 2022-03-15 13:00 | CURRENT | 1 | 0 |  |  | 2
| RO | 1854 | Error trying to delete subnet in AWS | v11.0 | OPEN-UNCONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:13 | CURRENT | 2022-01-10 14:13 | CURRENT | 2022-03-15 12:59 | assigned_to | 2022-03-15 12:59 | CURRENT | 1 | 0 |  |  | 2
| RO | 1855 | Error trying to name a resource in AWS during the creation | v11.0 | OPEN-UNCONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:15 | CURRENT | 2022-01-10 14:15 | CURRENT | 2022-03-15 12:59 | assigned_to | 2022-03-15 12:59 | CURRENT | 1 | 0 |  |  | 2
| RO | 1856 | User cannot define custom virtual-link-profile with IPv4 CIDR for AWS | v11.0 | OPEN-UNCONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:17 | CURRENT | 2022-01-10 14:17 | CURRENT | 2022-03-15 12:59 | assigned_to | 2022-03-15 12:59 | CURRENT | 1 | 0 |  |  | 2
| N2VC | 1857 | Nested Helm Chart resources cannot be scaled | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr | emin.aktas@ulakhaberlesme.com.tr | 2022-01-10 20:04 | CURRENT | 2022-01-10 20:04 | CURRENT | 2022-01-10 20:04 | comment | 2022-05-08 16:15 | RECENT | 1 | 0 |  |  | 1
| IM-NBI | 1869 | Endpoint - POST /nslcm/v1/ns_instances uses InstantiateNSRequest instead of CreateNSRequest | v10.0 | OPEN-UNCONFIRMED | rajeswari.kolluri@oracle.com |  | 2022-01-27 04:21 | CURRENT | 2022-01-27 04:21 | CURRENT |  | comment | 2022-01-27 04:21 | CURRENT | 1 | 0
| DEVOPS | 1874 | Docker Hub rate limit applies to additional hosts | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-02-02 13:29 | CURRENT | 2022-02-02 13:29 | CURRENT |  | comment | 2022-02-02 13:29 | CURRENT | 1 | 0
| N2VC | 1882 | LCM/N2VC error deploying KNF with 10 KDUs | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2022-02-15 16:32 | CURRENT | 2022-02-15 16:32 | CURRENT |  | dependson | 2022-02-15 16:32 | CURRENT | 1 | 0
| N2VC | 1883 | LCM/N2VC error deploying KNF with 10 KDUs | v11.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2022-02-15 16:32 | CURRENT | 2022-02-15 16:32 | CURRENT |  | comment | 2022-02-15 16:32 | CURRENT | 1 | 0
| N2VC | 1890 | Failed action does not show the failure message | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:43 | CURRENT | 2022-03-03 14:43 | CURRENT |  | comment | 2022-03-03 14:43 | CURRENT | 1 | 0
| N2VC | 1891 | Failed action does not show the failure message | v11.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:43 | CURRENT | 2022-03-03 14:43 | CURRENT |  | comment | 2022-03-03 14:43 | CURRENT | 1 | 0
| N2VC | 1892 | Failed action does not show the failure message | v10.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:43 | CURRENT | 2022-03-03 14:43 | CURRENT |  | comment | 2022-03-03 14:43 | CURRENT | 1 | 0
| NG-UI | 1893 | Action parameter name not being displayed | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:46 | CURRENT | 2022-03-03 14:46 | CURRENT |  | comment | 2022-04-06 11:57 | CURRENT | 1 | 0
| NG-UI | 1894 | Action parameter name not being displayed | v10.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:46 | CURRENT | 2022-03-03 14:46 | CURRENT |  | comment | 2022-04-06 13:20 | CURRENT | 1 | 0
| NG-UI | 1895 | Action parameter name not being displayed | v11.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:46 | CURRENT | 2022-03-03 14:46 | CURRENT |  | comment | 2022-04-06 13:21 | CURRENT | 1 | 0
| NG-UI | 1896 | Action parameter "application-name" not using default value for KDUs | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:51 | CURRENT | 2022-03-03 14:51 | CURRENT |  | comment | 2022-03-03 14:51 | CURRENT | 1 | 0
| NG-UI | 1897 | Action parameter "application-name" not using default value for KDUs | v10.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:51 | CURRENT | 2022-03-03 14:51 | CURRENT |  | comment | 2022-04-06 13:22 | CURRENT | 1 | 0
| NG-UI | 1898 | Action parameter "application-name" not using default value for KDUs | v11.0 | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:51 | CURRENT | 2022-03-03 14:51 | CURRENT |  | comment | 2022-04-06 13:22 | CURRENT | 1 | 0
| LCM | 1900 | WIM is not automatically selected and WIM parameters are not populated by the LCM component | v10.0 | IN_PROGRESS | lluis.gifre@cttc.es | lluis.gifre@cttc.es | 2022-03-04 17:30 | CURRENT | 2022-03-18 14:26 | CURRENT | 2022-03-07 14:00 | comment | 2022-05-02 18:08 | RECENT | 3 | 0 |  |  | 1
| DEVOPS | 1905 | Dependency error in Keystone | Master | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-03-10 10:25 | CURRENT | 2022-03-10 10:25 | CURRENT |  | blocked | 2022-03-10 10:27 | CURRENT | 1 | 0
| DEVOPS | 1906 | Dependency error in Keystone | v10.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-03-10 10:26 | CURRENT | 2022-03-10 10:26 | CURRENT |  | dependson | 2022-03-10 10:27 | CURRENT | 1 | 0
| DEVOPS | 1907 | Dependency error in Keystone | v11.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-03-10 10:27 | CURRENT | 2022-03-10 10:27 | CURRENT |  | comment | 2022-03-10 10:27 | CURRENT | 1 | 0
| RO | 1909 | Error deleting port: PortNotFoundClient | v11.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-03-11 11:52 | CURRENT | 2022-03-11 11:52 | CURRENT |  | comment | 2022-03-11 11:52 | CURRENT | 1 | 0