## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| N2VC | 1234 | OSM reports successful deployment when a charm relation fails | Master | CONFIRMED | endika.aldecoa@ehu.eus |  | 2020-09-25 12:29 | CURRENT | 2022-07-29 16:06 | RECENT |  | priority | 2022-07-29 16:06 | RECENT | 4 | 1 | 1
| LCM | 1579 | Error read ns record from database when execute action in function _on_update_n2vc_db | Master | OPEN-UNCONFIRMED | cuongbo97@gmail.com | glavado@whitestack.com | 2021-06-21 12:52 | CURRENT | 2021-06-21 12:52 | CURRENT | 2022-02-16 15:40 | comment | 2022-07-19 17:31 | CURRENT | 1 | 0 |  |  | 1
| RO | 1768 | GCP connector doesn't provide internet access for management network | Master | CONFIRMED | sgallardor@indra.es | sgallardor@indra.es | 2021-11-15 11:47 | CURRENT | 2021-12-13 11:54 | CURRENT | 2021-11-15 11:51 | comment | 2022-08-04 | RECENT | 2 | 0 |  |  | 1

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1123 | NS Instantiate nsName as required property [sol005robot] | Master | CONFIRMED | frank.bryden@etsi.org | gerardo.garciadeblas@telefonica.com | 2020-07-06 15:05 | CURRENT | 2022-06-28 17:30 | CURRENT | 2022-03-22 16:31 | resolution | 2022-06-28 17:30 | CURRENT | 3 | 1 | 1 |  | 3
| IM-NBI | 1188 | Uploading NSD content of NSD in state 'ONBOARDED' [sol005robot] | Master | CONFIRMED | frank.bryden@etsi.org | gerardo.garciadeblas@telefonica.com | 2020-08-10 16:34 | CURRENT | 2022-06-28 17:33 | CURRENT | 2022-03-22 16:34 | resolution | 2022-06-28 17:33 | CURRENT | 4 | 1 | 1 |  | 4
| IM-NBI | 1266 | Error on using object type parameter for actions from OSM | Master | CONFIRMED | preethika.p@tataelxsi.co.in | jmguzman@whitestack.com | 2020-10-19 06:41 | CURRENT | 2022-06-28 17:33 | CURRENT | 2021-12-10 10:21 | resolution | 2022-06-28 17:33 | CURRENT | 4 | 1 | 1 | 1 | 1
| IM-NBI | 1454 | OSM Performance Report missing Object descriptorType | Master | CONFIRMED | mark.beierl@canonical.com | agarcia@whitestack.com | 2021-02-25 17:49 | CURRENT | 2022-06-28 17:33 | CURRENT | 2021-07-08 17:41 | resolution | 2022-06-28 17:33 | CURRENT | 3 | 1 |  |  | 2
| IM-NBI | 1557 | Multiple VNFs using same VNFD ID at NSD can't connect to different networks | Master | OPEN-UNCONFIRMED | glavado@whitestack.com | gerardo.garciadeblas@telefonica.com | 2021-06-03 17:23 | CURRENT | 2021-06-03 17:23 | CURRENT | 2022-05-13 18:29 | comment | 2022-08-03 | RECENT | 1 | 0 |  |  | 4
| common | 1577 | NF/NS packages are not removed from LCM when the NS or NF is deleted | Master | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com | mark.beierl@canonical.com | 2021-06-18 17:02 | CURRENT | 2021-06-18 17:02 | CURRENT | 2022-02-16 15:46 | comment | 2022-08-09 | RECENT | 1 | 0 | 1 |  | 1
| IM-NBI | 1622 | Status report not consistent between NS and VNF | v10.0 | CONFIRMED | guillermo.gomez.external@atos.net | gerardo.garciadeblas@telefonica.com | 2021-08-02 10:41 | CURRENT | 2022-06-28 17:33 | CURRENT | 2022-03-28 17:20 | resolution | 2022-06-28 17:33 | CURRENT | 3 | 1 |  | 1 | 1
| N2VC | 1632 | Cannot add instantiation parameters for Juju bundles (KNF) | Master | CONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:52 | CURRENT | 2022-07-21 18:04 | CURRENT |  | version | 2022-07-21 18:04 | CURRENT | 3 | 1 | 1
| IM-NBI | 1752 | NBI does not validate manifest hashes from SOL004/SOL007 packages | v11.0 | CONFIRMED | fbravo@whitestack.com | gerardo.garciadeblas@telefonica.com | 2021-11-10 15:33 | CURRENT | 2022-06-28 17:31 | CURRENT | 2022-05-13 18:28 | resolution | 2022-06-28 17:31 | CURRENT | 3 | 1 |  |  | 3
| RO | 1769 | GCP connector doesn't provide internet access for management network | v11.0 | CONFIRMED | sgallardor@indra.es | sgallardor@indra.es | 2021-11-15 11:53 | CURRENT | 2021-12-13 11:54 | CURRENT | 2021-11-15 12:48 | comment | 2022-08-04 | RECENT | 2 | 0 |  |  | 1
| IM-NBI | 1808 | Validation in the NBI does not check mandatory fields | v11.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | jmguzman@whitestack.com | 2021-11-29 16:39 | CURRENT | 2022-06-28 17:31 | CURRENT | 2021-11-29 16:39 | resolution | 2022-06-28 17:31 | CURRENT | 3 | 1 |  |  | 1
| IM-NBI | 1825 | Create subscription problem | v10.0 | CONFIRMED | tolga.golelcin@telenity.com |  | 2021-12-13 11:09 | CURRENT | 2022-06-28 17:31 | CURRENT |  | resolution | 2022-06-28 17:31 | CURRENT | 3 | 1
| N2VC | 1857 | Nested Helm Chart resources cannot be scaled | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr | emin.aktas@ulakhaberlesme.com.tr | 2022-01-10 20:04 | CURRENT | 2022-01-10 20:04 | CURRENT | 2022-01-10 20:04 | comment | 2022-06-21 | CURRENT | 1 | 0 |  |  | 1
| LCM | 1900 | WIM is not automatically selected and WIM parameters are not populated by the LCM component | v10.0 | IN_PROGRESS | lluis.gifre@cttc.es | lluis.gifre@cttc.es | 2022-03-04 17:30 | CURRENT | 2022-03-18 14:26 | CURRENT | 2022-03-07 14:00 | keywords | 2022-08-04 | RECENT | 3 | 0 |  |  | 1
| LCM | 1921 | Helm EE has security risks | master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-03-21 20:13 | CURRENT | 2022-03-21 20:13 | CURRENT |  | comment | 2022-08-04 | RECENT | 1 | 0
| Robot-tests | 1931 | Missing parameter for k8s_11 | Master | OPEN-UNCONFIRMED | emin.aktas@ulakhaberlesme.com.tr | emin.aktas@ulakhaberlesme.com.tr | 2022-03-25 04:03 | CURRENT | 2022-03-25 04:03 | CURRENT | 2022-03-25 04:03 | comment | 2022-06-14 10:49 | CURRENT | 1 | 0 |  |  | 1
| NG-UI | 1936 | Strange NSI topology shown in UI | v11.0 | CONFIRMED | paranda@it.uc3m.es |  | 2022-03-26 12:44 | CURRENT | 2022-08-02 17:03 | RECENT |  | everconfirmed | 2022-08-02 17:03 | RECENT | 2 | 0
| MON | 1979 | MON deadlock occurs when scaling to more than 50vnfs | Master | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-04-05 10:36 | CURRENT | 2022-04-05 10:36 | CURRENT |  | comment | 2022-08-03 | RECENT | 1 | 0 | 1
| NG-UI | 1988 | Drop down for action does not reflect what the deployed service can actually do | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-04-09 04:04 | CURRENT | 2022-04-09 04:04 | CURRENT |  | keywords | 2022-08-04 00:01 | RECENT | 1 | 0
| LCM | 2042 | The VCA Status for an NS with both a KNF and a VNF does not provide the information of both | Master | IN_PROGRESS | escaleira@av.it.pt |  | 2022-05-21 20:41 | CURRENT | 2022-05-27 01:22 | CURRENT |  | comment | 2022-07-19 16:59 | CURRENT | 2 | 0
| LCM | 2043 | The VCA Status for an NS with both a KNF and a VNF does not provide the information of both | v11.0 | IN_PROGRESS | escaleira@av.it.pt |  | 2022-05-21 20:44 | CURRENT | 2022-05-31 01:32 | CURRENT |  | keywords | 2022-08-06 00:07 | RECENT | 2 | 0
| N2VC | 2069 | juju-bundle init failed when adding a k8s cluster to OSM | v10.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-06-09 12:05 | CURRENT | 2022-06-09 12:05 | CURRENT |  | comment | 2022-07-05 17:39 | CURRENT | 1 | 0
| RO | 2093 | Healing fails if the VM has a flavour that is not present in OpenStack | v12.0 | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-07-01 10:49 | CURRENT | 2022-07-01 10:49 | CURRENT |  | comment | 2022-07-01 10:49 | CURRENT | 1 | 0
| LCM | 2098 | VNF level manual healing through osmclient fails | v12.0 | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-07-05 14:29 | CURRENT | 2022-07-05 14:29 | CURRENT |  | comment | 2022-07-13 13:32 | CURRENT | 1 | 0
| IM-NBI | 2103 | Descriptor changes are validated for all the revisions although descriptor is not in use actively | v12.0 | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-07-07 17:49 | CURRENT | 2022-07-07 17:49 | CURRENT |  | comment | 2022-08-11 11:26 | RECENT | 1 | 0
| DEVOPS | 2125 | k8s monitor cannot install. | v12.0 | OPEN-UNCONFIRMED | tayloreisman2012@gmail.com | mark.beierl@canonical.com | 2022-07-24 02:42 | RECENT | 2022-07-24 02:42 | RECENT | 2022-08-02 16:53 | comment | 2022-08-10 21:29 | RECENT | 1 | 0 |  | 1 | 1

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1301 | Hardcoded credentials in code | v8.0 | OPEN-UNCONFIRMED | javier.ramon@telefonica.com | mark.beierl@canonical.com | 2020-11-27 15:55 | CURRENT | 2020-11-27 15:55 | CURRENT | 2021-10-26 16:44 | comment | 2022-08-04 | RECENT | 1 | 0 |  | 1 | 1
| RO | 1603 | Dummy VIM fails in HA configuration | v10.0 | CONFIRMED | mark.beierl@canonical.com | gulsum.atici@canonical.com | 2021-07-23 16:10 | CURRENT | 2022-06-07 16:53 | CURRENT | 2022-03-15 13:42 | comment | 2022-08-09 | RECENT | 3 | 0 |  |  | 2
| IM-NBI | 1660 | PATCH of /ns_descriptors/{nsdInfoId} returns wrong HTTP code[sol005robot] | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-14 17:26 | CURRENT | 2022-06-28 17:33 | CURRENT |  | resolution | 2022-06-28 17:33 | CURRENT | 3 | 1
| IM-NBI | 1661 | _id vs id [sol005robot] | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-14 17:30 | CURRENT | 2022-06-28 17:32 | CURRENT |  | resolution | 2022-06-28 17:32 | CURRENT | 3 | 1
| IM-NBI | 1667 | PATCH of Individual Package should return 200 [sol005robot] | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-16 17:09 | CURRENT | 2022-06-28 17:32 | CURRENT |  | resolution | 2022-06-28 17:32 | CURRENT | 3 | 1
| IM-NBI | 1668 | VNFPkgInfo contains more fields than required by default [sol005robot] | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-16 17:10 | CURRENT | 2022-06-28 17:32 | CURRENT |  | resolution | 2022-06-28 17:32 | CURRENT | 3 | 1
| IM-NBI | 1671 | Absence of id [sol005robot] | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:51 | CURRENT | 2022-06-28 17:32 | CURRENT |  | resolution | 2022-06-28 17:32 | CURRENT | 3 | 1
| IM-NBI | 1672 | Returned data on NsInstance creation does not conform [sol005robot] | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:52 | CURRENT | 2022-06-28 17:32 | CURRENT |  | resolution | 2022-06-28 17:32 | CURRENT | 3 | 1
| IM-NBI | 1673 | Launching multiple NS instances with single on-boarded NSD/VNFD just by varying values of IM's fields at NS instantiation time | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-09-20 21:53 | CURRENT | 2022-06-28 17:32 | CURRENT |  | resolution | 2022-06-28 17:32 | CURRENT | 3 | 1
| common | 1822 | Use mongodb client with asyncio support | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | mark.beierl@canonical.com | 2021-12-10 10:48 | CURRENT | 2021-12-10 10:48 | CURRENT | 2022-02-16 15:48 | comment | 2022-08-09 | RECENT | 1 | 0 |  |  | 1
| IM-NBI | 1829 | Missing "NsIdentifierDeletionNotification" notification [SOL005 V3.5.1] | v10.0 | CONFIRMED | rajeswari.kolluri@oracle.com |  | 2021-12-15 05:51 | CURRENT | 2022-06-28 17:31 | CURRENT |  | resolution | 2022-06-28 17:31 | CURRENT | 3 | 1
| IM-NBI | 1831 | OSM does not support few operations in NS instances and NS LCM | v11.0 | CONFIRMED | diksha.trehan@oracle.com |  | 2021-12-15 09:35 | CURRENT | 2022-06-28 17:31 | CURRENT |  | resolution | 2022-06-28 17:31 | CURRENT | 3 | 1 | 1
| RO | 1853 | Error trying to choose disk size for a new VDU in AWS | v11.0 | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:12 | CURRENT | 2022-06-06 22:47 | CURRENT | 2022-03-15 13:00 | comment | 2022-08-07 | RECENT | 2 | 0 |  |  | 2
| RO | 1855 | Error trying to name a resource in AWS during the creation | v11.0 | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:15 | CURRENT | 2022-06-06 22:44 | CURRENT | 2022-03-15 12:59 | comment | 2022-08-07 | RECENT | 2 | 0 |  |  | 2
| RO | 1856 | User cannot define custom virtual-link-profile with IPv4 CIDR for AWS | v11.0 | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:17 | CURRENT | 2022-06-06 22:43 | CURRENT | 2022-03-15 12:59 | comment | 2022-08-07 | RECENT | 2 | 0 |  |  | 2
| IM-NBI | 1869 | Endpoint - POST /nslcm/v1/ns_instances uses InstantiateNSRequest instead of CreateNSRequest | v10.0 | CONFIRMED | rajeswari.kolluri@oracle.com |  | 2022-01-27 04:21 | CURRENT | 2022-06-28 17:30 | CURRENT |  | resolution | 2022-06-28 17:30 | CURRENT | 3 | 1
| N2VC | 1890 | Failed action does not show the failure message | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com |  | 2022-03-03 14:43 | CURRENT | 2022-03-03 14:43 | CURRENT |  | comment | 2022-06-21 17:34 | CURRENT | 1 | 0
| OSMClient | 1935 | Autocompletion for BASH not created | v11.0 | CONFIRMED | paranda@it.uc3m.es |  | 2022-03-26 12:31 | CURRENT | 2022-08-10 16:17 | RECENT |  | everconfirmed | 2022-08-10 16:17 | RECENT | 2 | 0
| IM-NBI | 1942 | Facing an issue while instantiating Network Service after termination | v11.0 | OPEN-UNCONFIRMED | diksha.trehan@oracle.com |  | 2022-03-30 14:25 | CURRENT | 2022-03-30 14:25 | CURRENT |  | comment | 2022-08-03 | RECENT | 1 | 0 | 1
| IM-NBI | 1946 | LCM and NBI cannot connect to Mongo. Node is not in primary or recovering state | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2022-03-30 15:17 | CURRENT | 2022-06-28 17:30 | CURRENT |  | resolution | 2022-06-28 17:30 | CURRENT | 3 | 1
| NG-UI | 1952 | Uptime of running service instanced not displayed correctly | v11.0 | CONFIRMED | paranda@it.uc3m.es |  | 2022-03-31 12:06 | CURRENT | 2022-08-02 17:04 | RECENT |  | everconfirmed | 2022-08-02 17:04 | RECENT | 2 | 0
| IM-NBI | 1954 | The validation of the instantiation parameters does not include the auto-populated OSM parameter | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-03-31 12:43 | CURRENT | 2022-03-31 12:43 | CURRENT |  | comment | 2022-06-16 16:57 | CURRENT | 1 | 0
| IM-NBI | 1955 | The validation of the instantiation parameters does not include the auto-populated OSM parameter | v11.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-03-31 12:44 | CURRENT | 2022-03-31 12:44 | CURRENT |  | keywords | 2022-06-15 00:02 | CURRENT | 1 | 0
| IM-NBI | 1956 | The validation of the instantiation parameters does not include the auto-populated OSM parameter | v10.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-03-31 12:44 | CURRENT | 2022-03-31 12:44 | CURRENT |  | keywords | 2022-06-15 00:02 | CURRENT | 1 | 0 |  | 1
| IM-NBI | 1970 | The Dockerfile.local Ubuntu version causes the installation of the Python requirements to fail | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-04-03 19:25 | CURRENT | 2022-04-03 19:25 | CURRENT |  | comment | 2022-06-20 18:39 | CURRENT | 1 | 0
| IM-NBI | 1971 | The Dockerfile.local Ubuntu version causes the installation of the Python requirements to fail | v11.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-04-03 19:26 | CURRENT | 2022-04-03 19:26 | CURRENT |  | keywords | 2022-06-15 00:02 | CURRENT | 1 | 0
| IM-NBI | 1972 | The Dockerfile.local Ubuntu version causes the installation of the Python requirements to fail | v10.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-04-03 19:28 | CURRENT | 2022-04-03 19:28 | CURRENT |  | keywords | 2022-06-15 00:02 | CURRENT | 1 | 0
| IM-NBI | 2009 | Errors in instance_topic.py:_check_vnf_instantiation_params when trying to use existing volumes as instantiation parameters | v11.0 | OPEN-UNCONFIRMED | garomero@indra.es |  | 2022-04-25 15:57 | CURRENT | 2022-04-25 15:57 | CURRENT |  | comment | 2022-06-20 15:42 | CURRENT | 1 | 0
| Gerrit | 2015 | Gerrit no longer closing bugs when patch are merged | unspecified | OPEN-UNCONFIRMED | silvia.almagia@etsi.org |  | 2022-04-26 16:58 | CURRENT | 2022-04-26 16:58 | CURRENT |  | keywords | 2022-08-10 11:03 | RECENT | 1 | 0
| RO | 2019 | Onos-vpls plugin should delete ONOS hosts when the NS is deleted | v11.0 | OPEN-UNCONFIRMED | glavado@whitestack.com |  | 2022-04-28 16:54 | CURRENT | 2022-04-28 16:54 | CURRENT |  | keywords | 2022-08-04 00:01 | RECENT | 1 | 0
| RO | 2020 | SDN Assist data sent to SDN Controller might get outdated because of Nova Rescheduling | v11.0 | OPEN-UNCONFIRMED | glavado@whitestack.com |  | 2022-04-28 17:04 | CURRENT | 2022-04-28 17:04 | CURRENT |  | keywords | 2022-08-04 00:01 | RECENT | 1 | 0
| IM-NBI | 2038 | Additional params not accepted for Hybrid Network Functions | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-05-20 16:20 | CURRENT | 2022-05-20 16:20 | CURRENT |  | comment | 2022-06-30 14:49 | CURRENT | 1 | 0
| IM-NBI | 2039 | Additional params not accepted for Hybrid Network Functions | v11.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-05-20 16:38 | CURRENT | 2022-05-20 16:38 | CURRENT |  | comment | 2022-06-30 14:49 | CURRENT | 1 | 0
| IM-NBI | 2040 | Additional params not accepted for Hybrid Network Functions | v10.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-05-20 16:39 | CURRENT | 2022-05-20 16:39 | CURRENT |  | comment | 2022-06-30 14:49 | CURRENT | 1 | 0
| LCM | 2044 | The VCA Status for an NS with both a KNF and a VNF does not provide the information of both | v10.0 | IN_PROGRESS | escaleira@av.it.pt |  | 2022-05-21 20:44 | CURRENT | 2022-05-31 01:32 | CURRENT |  | keywords | 2022-08-06 00:07 | RECENT | 2 | 0
| LCM | 2049 | Scaling methodology failure | v11.0 | OPEN-UNCONFIRMED | pooja.r@tataelxsi.co.in |  | 2022-05-26 18:00 | CURRENT | 2022-05-26 18:00 | CURRENT |  | comment | 2022-07-19 17:39 | CURRENT | 1 | 0
| N2VC | 2063 | The Helm Charts based KNF scaling count operation is faulty | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-03 18:59 | CURRENT | 2022-07-07 17:16 | CURRENT |  | comment | 2022-07-07 17:24 | CURRENT | 2 | 0
| N2VC | 2065 | N2VC fails to scale a KNF based on Helm Charts, when the values were passed through file and not through command | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-04 19:36 | CURRENT | 2022-07-07 17:16 | CURRENT |  | everconfirmed | 2022-07-07 17:16 | CURRENT | 2 | 0
| N2VC | 2066 | The edge case of first scaling down an Helm Chart, and then scaling up, is causing misleading behavior in the scale up operation | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-04 22:31 | CURRENT | 2022-07-07 17:16 | CURRENT |  | comment | 2022-07-08 00:03 | CURRENT | 2 | 0
| IM-NBI | 2068 | show_content_artifacts error for zip uploaded packages (sol004 and sol007) | v11.0 | OPEN-UNCONFIRMED | selvi.j@tataelxsi.co.in |  | 2022-06-07 09:30 | CURRENT | 2022-06-07 09:30 | CURRENT |  | comment | 2022-08-08 | RECENT | 1 | 0
| N2VC | 2070 | juju-bundle init failed when adding a k8s cluster to OSM | v11.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-06-09 12:06 | CURRENT | 2022-06-09 12:06 | CURRENT |  | keywords | 2022-08-11 00:01 | RECENT | 1 | 0
| N2VC | 2071 | juju-bundle init failed when adding a k8s cluster to OSM | Master | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-06-09 12:07 | CURRENT | 2022-06-09 12:07 | CURRENT |  | keywords | 2022-08-11 00:01 | RECENT | 1 | 0
| OSMClient | 2074 | "osm repo-index" command deletes package directories | v10.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2022-06-10 13:14 | CURRENT | 2022-06-10 13:14 | CURRENT |  | comment | 2022-08-10 16:36 | RECENT | 1 | 0