## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1622 | Status report not consistent between NS and VNF | v10.0 | CONFIRMED | guillermo.gomez.external@atos.net | gerardo.garciadeblas@telefonica.com | 2021-08-02 10:41 | CURRENT | 2022-10-04 17:58 | RECENT | 2022-03-28 17:20 | keywords | 2022-10-04 18:00 | RECENT | 5 | 2 |  | 1 | 1
| LCM | 2140 | can't touch a file because the permission error of mongodb | v12.0 | OPEN-UNCONFIRMED | abigailxiang@outlook.com |  | 2022-08-17 11:44 | CURRENT | 2022-08-17 11:44 | CURRENT |  | comment | 2022-08-24 19:51 | CURRENT | 1 | 0

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1123 | NS Instantiate nsName as required property [sol005robot] | Master | CONFIRMED | frank.bryden@etsi.org | gerardo.garciadeblas@telefonica.com | 2020-07-06 15:05 | CURRENT | 2022-10-04 17:47 | RECENT | 2022-03-22 16:31 | resolution | 2022-10-04 17:47 | RECENT | 5 | 2 | 1 |  | 3
| IM-NBI | 1188 | Uploading NSD content of NSD in state 'ONBOARDED' [sol005robot] | Master | CONFIRMED | frank.bryden@etsi.org | gerardo.garciadeblas@telefonica.com | 2020-08-10 16:34 | CURRENT | 2022-10-04 17:48 | RECENT | 2022-03-22 16:34 | keywords | 2022-10-04 17:56 | RECENT | 6 | 2 | 1 |  | 4
| N2VC | 1234 | OSM reports successful deployment when a charm relation fails | Master | CONFIRMED | endika.aldecoa@ehu.eus |  | 2020-09-25 12:29 | CURRENT | 2022-07-29 16:06 | CURRENT |  | keywords | 2022-09-08 19:58 | CURRENT | 4 | 1 | 1
| common | 1577 | NF/NS packages are not removed from LCM when the NS or NF is deleted | Master | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com | gulsum.atici@canonical.com | 2021-06-18 17:02 | CURRENT | 2021-06-18 17:02 | CURRENT | 2022-10-20 23:01 | priority | 2022-10-20 23:01 | RECENT | 1 | 0 | 1 | 2 | 3
| N2VC | 1584 | Failure updating the ns state with distributed VCA | Master | UNCONFIRMED | david.garcia@canonical.com |  | 2021-06-22 11:27 | CURRENT | 2022-08-16 17:57 | CURRENT |  | comment | 2022-10-17 | RECENT | 3 | 1
| IM-NBI | 1752 | NBI does not validate manifest hashes from SOL004/SOL007 packages | v12.0 | CONFIRMED | fbravo@whitestack.com | starazona@whitestack.com | 2021-11-10 15:33 | CURRENT | 2022-06-28 17:31 | CURRENT | 2022-09-20 17:36 | keywords | 2022-09-21 | CURRENT | 3 | 1 | 1 |  | 4
| RO | 1768 | GCP connector doesn't provide internet access for management network | Master | CONFIRMED | sgallardor@indra.es | gulsum.atici@canonical.com | 2021-11-15 11:47 | CURRENT | 2022-09-02 09:05 | CURRENT | 2022-09-02 09:05 | resolution | 2022-09-02 09:05 | CURRENT | 4 | 1 |  |  | 2
| LCM | 1921 | Helm EE has security risks | master | IN_PROGRESS | mark.beierl@canonical.com | gcuba@whitestack.com | 2022-03-21 20:13 | CURRENT | 2022-10-14 20:57 | RECENT | 2022-09-02 09:02 | priority | 2022-10-14 20:57 | RECENT | 4 | 1 |  |  | 1
| MON | 1979 | MON deadlock occurs when scaling to more than 50vnfs | v12.0 | UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-04-05 10:36 | CURRENT | 2022-09-08 06:17 | CURRENT |  | comment | 2022-09-08 06:46 | CURRENT | 3 | 1 | 2
| NG-UI | 1988 | Drop down for action does not reflect what the deployed service can actually do | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-04-09 04:04 | CURRENT | 2022-04-09 04:04 | CURRENT |  | keywords | 2022-10-14 | RECENT | 1 | 0
| LCM | 2087 | Fail to add juju relation OSM 11.02 | v11.0 | IN_PROGRESS | david.franco@ehu.eus |  | 2022-06-21 18:25 | CURRENT | 2022-09-19 08:07 | CURRENT |  | comment | 2022-10-14 01:23 | RECENT | 3 | 0
| RO | 2093 | Healing fails if the VM has a flavour that is not present in OpenStack | v12.0 | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-07-01 10:49 | CURRENT | 2022-07-01 10:49 | CURRENT |  | keywords | 2022-09-05 00:01 | CURRENT | 1 | 0
| LCM | 2096 | A user is not able to use a VDU/KDU scaling config primitive | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-07-04 16:37 | CURRENT | 2022-07-04 16:37 | CURRENT |  | short_desc | 2022-09-07 15:10 | CURRENT | 1 | 0
| LCM | 2124 | When scaling a KDU, the timeout set for waiting for the N2VC method scale is below the default timeout used in the corresponding scale command | Master | IN_PROGRESS | escaleira@av.it.pt |  | 2022-07-23 21:56 | CURRENT | 2022-09-02 19:29 | CURRENT |  | priority | 2022-09-06 02:07 | CURRENT | 2 | 0
| DEVOPS | 2125 | k8s monitor cannot install. | v12.0 | OPEN-UNCONFIRMED | tayloreisman2012@gmail.com | mark.beierl@canonical.com | 2022-07-24 02:42 | CURRENT | 2022-07-24 02:42 | CURRENT | 2022-08-02 16:53 | comment | 2022-10-11 00:01 | RECENT | 1 | 0 |  | 1 | 1
| DEVOPS | 2143 | Errors while installing helm are not properly tracked | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2022-08-18 16:58 | CURRENT | 2022-08-18 16:58 | CURRENT |  | comment | 2022-09-30 12:01 | RECENT | 1 | 0
| NG-UI | 2148 | VDU Id issue & Multivdu Count Index Error in VM Action | v12.0 | OPEN-UNCONFIRMED | sandhya.j@tataelxsi.co.in |  | 2022-08-25 04:27 | CURRENT | 2022-08-25 04:27 | CURRENT |  | comment | 2022-09-07 12:15 | CURRENT | 1 | 0
| LCM | 2161 | The instantiation of a KNF whose NS parameter vimAccountId causes LCM to throw an exception and the instantiation to fail | v12.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-09-12 00:58 | CURRENT | 2022-09-12 00:58 | CURRENT |  | comment | 2022-09-12 00:58 | CURRENT | 1 | 0
| LCM | 2163 | The instantiation of a KNF whose NS parameter vimAccountId causes LCM to throw an exception and the instantiation to fail | v10.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-09-12 00:59 | CURRENT | 2022-09-12 00:59 | CURRENT |  | comment | 2022-09-12 00:59 | CURRENT | 1 | 0
| OSMClient | 2176 | vca-update using ID modifies the name of the VCA on DB | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-09-30 14:47 | RECENT | 2022-09-30 14:47 | RECENT |  | comment | 2022-09-30 14:47 | RECENT | 1 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1266 | Error on using object type parameter for actions from OSM | Master | CONFIRMED | preethika.p@tataelxsi.co.in | jmguzman@whitestack.com | 2020-10-19 06:41 | CURRENT | 2022-10-04 17:55 | RECENT | 2021-12-10 10:21 | resolution | 2022-10-04 17:55 | RECENT | 6 | 2 | 1 | 1 | 1
| IM-NBI | 1301 | Hardcoded credentials in code | v8.0 | CONFIRMED | javier.ramon@telefonica.com | mark.beierl@canonical.com | 2020-11-27 15:55 | CURRENT | 2022-09-03 03:21 | CURRENT | 2021-10-26 16:44 | resolution | 2022-09-03 03:21 | CURRENT | 3 | 1 |  | 1 | 1
| IM-NBI | 1454 | OSM Performance Report missing Object descriptorType | Master | CONFIRMED | mark.beierl@canonical.com | agarcia@whitestack.com | 2021-02-25 17:49 | CURRENT | 2022-10-04 17:56 | RECENT | 2021-07-08 17:41 | resolution | 2022-10-04 17:56 | RECENT | 5 | 2 |  |  | 2
| RO | 1603 | Dummy VIM fails in HA configuration | v10.0 | CONFIRMED | mark.beierl@canonical.com | gulsum.atici@canonical.com | 2021-07-23 16:10 | CURRENT | 2022-06-07 16:53 | CURRENT | 2022-03-15 13:42 | comment | 2022-09-28 00:01 | CURRENT | 3 | 0 |  |  | 2
| N2VC | 1630 | Cannot add instantiation parameters for Juju bundles (KNF) | Master | CONFIRMED | david.garcia@canonical.com |  | 2021-08-09 16:50 | CURRENT | 2022-08-16 17:56 | CURRENT |  | comment | 2022-10-17 | RECENT | 3 | 1
| IM-NBI | 1808 | Validation in the NBI does not check mandatory fields | v12.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | jmguzman@whitestack.com | 2021-11-29 16:39 | CURRENT | 2022-06-28 17:31 | CURRENT | 2021-11-29 16:39 | version | 2022-08-23 17:56 | CURRENT | 3 | 1 | 1 |  | 1
| common | 1822 | Use mongodb client with asyncio support | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | mark.beierl@canonical.com | 2021-12-10 10:48 | CURRENT | 2021-12-10 10:48 | CURRENT | 2022-02-16 15:48 | keywords | 2022-09-05 00:01 | CURRENT | 1 | 0 |  |  | 1
| IM-NBI | 1825 | Create subscription problem | v10.0 | CONFIRMED | tolga.golelcin@telenity.com |  | 2021-12-13 11:09 | CURRENT | 2022-06-28 17:31 | CURRENT |  | keywords | 2022-09-21 00:01 | CURRENT | 3 | 1
| IM-NBI | 1829 | Missing "NsIdentifierDeletionNotification" notification [SOL005 V3.5.1] | v10.0 | CONFIRMED | rajeswari.kolluri@oracle.com |  | 2021-12-15 05:51 | CURRENT | 2022-06-28 17:31 | CURRENT |  | keywords | 2022-09-21 00:01 | CURRENT | 3 | 1
| RO | 1853 | Error trying to choose disk size for a new VDU in AWS | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:12 | CURRENT | 2022-06-06 22:47 | CURRENT | 2022-03-15 13:00 | keywords | 2022-09-05 00:01 | CURRENT | 2 | 0 | 1 |  | 2
| RO | 1855 | Error trying to name a resource in AWS during the creation | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:15 | CURRENT | 2022-06-06 22:44 | CURRENT | 2022-03-15 12:59 | keywords | 2022-09-05 00:01 | CURRENT | 2 | 0 | 1 |  | 2
| RO | 1856 | User cannot define custom virtual-link-profile with IPv4 CIDR for AWS | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:17 | CURRENT | 2022-06-06 22:43 | CURRENT | 2022-03-15 12:59 | keywords | 2022-09-05 00:01 | CURRENT | 2 | 0 | 1 |  | 2
| IM-NBI | 1869 | Endpoint - POST /nslcm/v1/ns_instances uses InstantiateNSRequest instead of CreateNSRequest | v10.0 | CONFIRMED | rajeswari.kolluri@oracle.com |  | 2022-01-27 04:21 | CURRENT | 2022-06-28 17:30 | CURRENT |  | keywords | 2022-09-21 00:01 | CURRENT | 3 | 1
| OSMClient | 1935 | Autocompletion for BASH not created | v11.0 | CONFIRMED | paranda@it.uc3m.es |  | 2022-03-26 12:31 | CURRENT | 2022-08-10 16:17 | CURRENT |  | comment | 2022-10-11 | RECENT | 2 | 0
| IM-NBI | 1954 | The validation of the instantiation parameters does not include the auto-populated OSM parameter | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-03-31 12:43 | CURRENT | 2022-08-23 16:14 | CURRENT |  | keywords | 2022-08-24 | CURRENT | 2 | 0
| IM-NBI | 1970 | The Dockerfile.local Ubuntu version causes the installation of the Python requirements to fail | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-04-03 19:25 | CURRENT | 2022-08-23 16:17 | CURRENT |  | keywords | 2022-08-24 00:01 | CURRENT | 2 | 0
| Gerrit | 2015 | Gerrit no longer closing bugs when patch are merged | unspecified | OPEN-UNCONFIRMED | silvia.almagia@etsi.org |  | 2022-04-26 16:58 | CURRENT | 2022-04-26 16:58 | CURRENT |  | comment | 2022-10-11 | RECENT | 1 | 0
| RO | 2019 | Onos-vpls plugin should delete ONOS hosts when the NS is deleted | v11.0 | OPEN-UNCONFIRMED | glavado@whitestack.com |  | 2022-04-28 16:54 | CURRENT | 2022-04-28 16:54 | CURRENT |  | comment | 2022-10-05 | RECENT | 1 | 0
| RO | 2020 | SDN Assist data sent to SDN Controller might get outdated because of Nova Rescheduling | v11.0 | OPEN-UNCONFIRMED | glavado@whitestack.com |  | 2022-04-28 17:04 | CURRENT | 2022-04-28 17:04 | CURRENT |  | comment | 2022-10-05 | RECENT | 1 | 0
| IM-NBI | 2038 | Additional params not accepted for Hybrid Network Functions | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-05-20 16:20 | CURRENT | 2022-08-23 16:16 | CURRENT |  | comment | 2022-10-11 17:59 | RECENT | 2 | 0
| N2VC | 2063 | The Helm Charts based KNF scaling count operation is faulty | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-03 18:59 | CURRENT | 2022-07-07 17:16 | CURRENT |  | keywords | 2022-10-05 | RECENT | 2 | 0
| N2VC | 2066 | The edge case of first scaling down an Helm Chart, and then scaling up, is causing misleading behavior in the scale up operation | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-04 22:31 | CURRENT | 2022-07-07 17:16 | CURRENT |  | comment | 2022-10-14 13:57 | RECENT | 2 | 0
| LCM | 2083 | Helm Chart based EE has access to the overall OSM infrastructure | master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-18 13:58 | CURRENT | 2022-06-20 06:31 | CURRENT |  | comment | 2022-10-10 | RECENT | 2 | 0
| LCM | 2088 | Remote Code Execution in N2VC/LCM | master | CONFIRMED | escaleira@av.it.pt | gcuba@whitestack.com | 2022-06-21 20:10 | CURRENT | 2022-08-30 16:54 | CURRENT | 2022-08-30 16:54 | everconfirmed | 2022-08-30 16:54 | CURRENT | 2 | 0 |  | 1 | 1
| IM-NBI | 2089 | The IM relational-operation-type entry in the common augments should also enumerate the NE operator | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-06-28 16:46 | CURRENT | 2022-06-28 16:46 | CURRENT |  | comment | 2022-08-23 17:07 | CURRENT | 1 | 0
| NG-UI | 2091 | NS Update on NS Instances fail with database exception on screen when VNFD ID is incorrect | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-06-29 20:14 | CURRENT | 2022-06-29 20:14 | CURRENT |  | comment | 2022-09-07 12:15 | CURRENT | 1 | 0
| IM-NBI | 2094 | A user is not able to use a VDU/KDU scaling config primitive | v12.0 | CONFIRMED | escaleira@av.it.pt | gerardo.garciadeblas@telefonica.com | 2022-07-04 16:36 | CURRENT | 2022-09-20 17:15 | CURRENT | 2022-09-04 13:29 | bug_severity | 2022-09-20 17:34 | CURRENT | 2 | 0 | 1 | 1 | 1
| IM-NBI | 2095 | A user is not able to use a VDU/KDU scaling config primitive | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-07-04 16:37 | CURRENT | 2022-09-07 15:31 | CURRENT |  | bug_severity | 2022-09-20 17:34 | CURRENT | 2 | 0
| IM-NBI | 2103 | Descriptor changes are validated for all the revisions although descriptor is not in use actively | v12.0 | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-07-07 17:49 | CURRENT | 2022-07-07 17:49 | CURRENT |  | comment | 2022-10-11 17:54 | RECENT | 1 | 0
| N2VC | 2104 | When we have more than one scalable resources in an Helm Based KNF, the scaling of one sets the other ones to the default value | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-07-07 21:46 | CURRENT | 2022-07-07 21:46 | CURRENT |  | comment | 2022-10-11 19:30 | RECENT | 1 | 0
| N2VC | 2105 | When we have more than one scalable resources in an Helm Based KNF, the scaling of one sets the other ones to the default value | v12.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-07-07 21:48 | CURRENT | 2022-07-07 21:48 | CURRENT |  | comment | 2022-09-22 09:39 | CURRENT | 1 | 0
| N2VC | 2106 | N2VC fails to scale a KNF based on Helm Charts, when the values were passed through file and not through command | v12.0 | CONFIRMED | escaleira@av.it.pt |  | 2022-07-07 23:41 | CURRENT | 2022-10-07 09:28 | RECENT |  | resolution | 2022-10-07 09:28 | RECENT | 3 | 1
| N2VC | 2107 | The edge case of first scaling down an Helm Chart, and then scaling up, is causing misleading behavior in the scale up operation | v12.0 | CONFIRMED | escaleira@av.it.pt |  | 2022-07-07 23:43 | CURRENT | 2022-10-07 09:29 | RECENT |  | resolution | 2022-10-07 09:29 | RECENT | 3 | 1
| RO | 2109 | RO creates a copy of VIM details in VDUR section instead of updating existing VIM details in VIM info | v12.0 | OPEN-UNCONFIRMED | deepika.e@tataelxsi.co.in |  | 2022-07-08 14:56 | CURRENT | 2022-07-08 14:56 | CURRENT |  | keywords | 2022-09-21 00:01 | CURRENT | 1 | 0
| MON | 2111 | MON error if more than a few hundreds VM provisioned, even if metrics are not specified in the descriptors | v10.0 | OPEN-UNCONFIRMED | frodriguezg@indra.es |  | 2022-07-11 14:24 | CURRENT | 2022-07-11 14:24 | CURRENT |  | keywords | 2022-09-14 00:01 | CURRENT | 1 | 0
| N2VC | 2117 | Day-2 primitives based on helm charts EE fail | Master | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com | guillermo.calvino@canonical.com | 2022-07-13 13:26 | CURRENT | 2022-07-13 13:26 | CURRENT | 2022-07-14 15:54 | keywords | 2022-09-16 00:01 | CURRENT | 1 | 0 |  | 1 | 2
| MON | 2120 | Wrong usage of Multiprocessing and AsyncIO is causing performance issues | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-07-20 13:00 | CURRENT | 2022-07-20 13:00 | CURRENT |  | keywords | 2022-10-05 00:01 | RECENT | 1 | 0
| NG-UI | 2121 | NG-UI uses unmaintained Chokidar version | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-07-20 17:29 | CURRENT | 2022-07-20 17:29 | CURRENT |  | cc | 2022-08-25 08:47 | CURRENT | 1 | 0
| LCM | 2130 | TOC-TOU in scaling operations for the same VNF/VNF instance | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-07-29 18:48 | CURRENT | 2022-09-06 02:07 | CURRENT |  | comment | 2022-09-06 10:54 | CURRENT | 2 | 0
| DEVOPS | 2131 | Cannot install OSM due to Failed to bootstrap controller osm | v12.0 | OPEN-UNCONFIRMED | abigailxiang@outlook.com | mark.beierl@canonical.com | 2022-08-01 14:56 | CURRENT | 2022-08-01 14:56 | CURRENT | 2022-08-02 16:52 | comment | 2022-10-03 | RECENT | 1 | 0 |  | 1 | 1
| IM-NBI | 2134 | "_admin:usageState" is not updated properly in VNF and NS Descriptors | v12.0 | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-08-10 11:11 | CURRENT | 2022-08-10 11:11 | CURRENT |  | comment | 2022-10-11 17:54 | RECENT | 1 | 0
| LCM | 2144 | Cannot delete an NS if there are pending actions | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-08-18 20:35 | CURRENT | 2022-08-18 20:35 | CURRENT |  | keywords | 2022-10-20 | RECENT | 1 | 0