## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| LCM | 1577 | NF/NS packages are not removed from LCM when the NS or NF is deleted | Master | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com | gcuba@whitestack.com | 2021-06-18 17:02 | CURRENT | 2021-06-18 17:02 | CURRENT | 2022-12-01 09:59 | component | 2022-12-01 09:59 | CURRENT | 1 | 0 | 1 | 3 | 4

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| N2VC | 1234 | OSM reports successful deployment when a charm relation fails | Master | CONFIRMED | endika.aldecoa@ehu.eus |  | 2020-09-25 12:29 | CURRENT | 2022-07-29 16:06 | CURRENT |  | comment | 2023-01-04 22:46 | RECENT | 4 | 1 | 1
| RO | 1603 | Dummy VIM fails in HA configuration | Master | CONFIRMED | mark.beierl@canonical.com | gulsum.atici@canonical.com | 2021-07-23 16:10 | CURRENT | 2022-06-07 16:53 | CURRENT | 2022-03-15 13:42 | version | 2022-12-01 10:04 | CURRENT | 3 | 0 | 1 |  | 2
| RO | 1768 | GCP connector doesn't provide internet access for management network | Master | CONFIRMED | sgallardor@indra.es | gulsum.atici@canonical.com | 2021-11-15 11:47 | CURRENT | 2022-09-02 09:05 | CURRENT | 2022-09-02 09:05 | comment | 2022-12-01 10:21 | CURRENT | 4 | 1 |  |  | 2
| LCM | 1921 | Helm EE has security risks | master | IN_PROGRESS | mark.beierl@canonical.com | gcuba@whitestack.com | 2022-03-21 20:13 | CURRENT | 2022-10-14 20:57 | CURRENT | 2022-09-02 09:02 | keywords | 2022-12-15 06:23 | CURRENT | 4 | 1 |  |  | 1
| IM-NBI | 1954 | The validation of the instantiation parameters does not include the auto-populated OSM parameter | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-03-31 12:43 | CURRENT | 2022-08-23 16:14 | CURRENT |  | keywords | 2022-11-23 00:01 | CURRENT | 2 | 0
| NG-UI | 1988 | Drop down for action does not reflect what the deployed service can actually do | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-04-09 04:04 | CURRENT | 2022-04-09 04:04 | CURRENT |  | comment | 2023-01-05 22:09 | RECENT | 1 | 0
| RO | 2093 | Healing fails if the VM has a flavour that is not present in OpenStack | v12.0 | IN_PROGRESS | priyadarshini@tataelxsi.co.in |  | 2022-07-01 10:49 | CURRENT | 2022-11-28 23:21 | CURRENT |  | everconfirmed | 2022-11-28 23:21 | CURRENT | 2 | 0
| IM-NBI | 2103 | Descriptor changes are validated for all the revisions although descriptor is not in use actively | v12.0 | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-07-07 17:49 | CURRENT | 2022-07-07 17:49 | CURRENT |  | comment | 2022-12-12 | CURRENT | 1 | 0
| DEVOPS | 2143 | Errors while installing helm are not properly tracked | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2022-08-18 16:58 | CURRENT | 2022-08-18 16:58 | CURRENT |  | comment | 2022-11-16 11:44 | CURRENT | 1 | 0
| LCM | 2165 | Upgrading charms KNF package doesn't work if the new package folder has a different name | v12.0 | CONFIRMED | daguilarh@indra.es |  | 2022-09-14 12:56 | CURRENT | 2022-12-15 06:21 | CURRENT |  | resolution | 2022-12-15 06:21 | CURRENT | 3 | 1
| OSMClient | 2176 | vca-update using ID modifies the name of the VCA on DB | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-09-30 14:47 | CURRENT | 2022-09-30 14:47 | CURRENT |  | keywords | 2022-12-07 00:01 | CURRENT | 1 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 1301 | Hardcoded credentials in code | v8.0 | CONFIRMED | javier.ramon@telefonica.com | mark.beierl@canonical.com | 2020-11-27 15:55 | CURRENT | 2022-09-03 03:21 | CURRENT | 2021-10-26 16:44 | keywords | 2023-01-06 | RECENT | 3 | 1 |  | 1 | 1
| common | 1822 | Use mongodb client with asyncio support | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | mark.beierl@canonical.com | 2021-12-10 10:48 | CURRENT | 2021-12-10 10:48 | CURRENT | 2022-02-16 15:48 | keywords | 2022-11-29 | CURRENT | 1 | 0 |  |  | 1
| RO | 1853 | Error trying to choose disk size for a new VDU in AWS | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:12 | CURRENT | 2022-06-06 22:47 | CURRENT | 2022-03-15 13:00 | keywords | 2022-11-29 | CURRENT | 2 | 0 | 1 |  | 2
| RO | 1855 | Error trying to name a resource in AWS during the creation | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:15 | CURRENT | 2022-06-06 22:44 | CURRENT | 2022-03-15 12:59 | keywords | 2022-11-29 00:01 | CURRENT | 2 | 0 | 1 |  | 2
| RO | 1856 | User cannot define custom virtual-link-profile with IPv4 CIDR for AWS | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:17 | CURRENT | 2022-06-06 22:43 | CURRENT | 2022-03-15 12:59 | keywords | 2022-11-29 00:01 | CURRENT | 2 | 0 | 1 |  | 2
| Gerrit | 2015 | Gerrit no longer closing bugs when patch are merged | unspecified | CONFIRMED | silvia.almagia@etsi.org |  | 2022-04-26 16:58 | CURRENT | 2022-11-21 14:53 | CURRENT |  | resolution | 2022-11-21 14:53 | CURRENT | 3 | 1
| RO | 2019 | Onos-vpls plugin should delete ONOS hosts when the NS is deleted | v11.0 | CONFIRMED | glavado@whitestack.com |  | 2022-04-28 16:54 | CURRENT | 2022-11-08 16:42 | CURRENT |  | resolution | 2022-11-08 16:42 | CURRENT | 3 | 1
| RO | 2020 | SDN Assist data sent to SDN Controller might get outdated because of Nova Rescheduling | Master | CONFIRMED | glavado@whitestack.com |  | 2022-04-28 17:04 | CURRENT | 2022-11-08 16:42 | CURRENT |  | version | 2022-11-29 15:07 | CURRENT | 3 | 1 | 1
| IM-NBI | 2038 | Additional params not accepted for Hybrid Network Functions | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-05-20 16:20 | CURRENT | 2022-08-23 16:16 | CURRENT |  | comment | 2022-12-26 | RECENT | 2 | 0
| N2VC | 2063 | The Helm Charts based KNF scaling count operation is faulty | Master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-03 18:59 | CURRENT | 2022-07-07 17:16 | CURRENT |  | keywords | 2022-12-13 | CURRENT | 2 | 0
| LCM | 2083 | Helm Chart based EE has access to the overall OSM infrastructure | master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-18 13:58 | CURRENT | 2022-11-08 14:32 | CURRENT |  | resolution | 2022-11-08 14:32 | CURRENT | 4 | 1
| RO | 2109 | RO creates a copy of VIM details in VDUR section instead of updating existing VIM details in VIM info | v12.0 | OPEN-UNCONFIRMED | deepika.e@tataelxsi.co.in |  | 2022-07-08 14:56 | CURRENT | 2022-07-08 14:56 | CURRENT |  | keywords | 2022-11-29 00:01 | CURRENT | 1 | 0
| MON | 2120 | Wrong usage of Multiprocessing and AsyncIO is causing performance issues | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2022-07-20 13:00 | CURRENT | 2022-07-20 13:00 | CURRENT |  | comment | 2022-11-27 20:32 | CURRENT | 1 | 0
| NG-UI | 2121 | NG-UI uses unmaintained Chokidar version | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-07-20 17:29 | CURRENT | 2022-07-20 17:29 | CURRENT |  | keywords | 2023-01-04 | RECENT | 1 | 0
| IM-NBI | 2134 | "_admin:usageState" is not updated properly in VNF and NS Descriptors | v12.0 | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-08-10 11:11 | CURRENT | 2022-08-10 11:11 | CURRENT |  | comment | 2022-12-12 00:01 | CURRENT | 1 | 0
| LCM | 2144 | Cannot delete an NS if there are pending actions | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-08-18 20:35 | CURRENT | 2022-08-18 20:35 | CURRENT |  | keywords | 2023-01-04 | RECENT | 1 | 0
| RO | 2147 | net_type always bridge because no underlay information is provided | v12.0 | OPEN-UNCONFIRMED | srodriguez@optaresolutions.com |  | 2022-08-24 17:48 | CURRENT | 2022-08-24 17:48 | CURRENT |  | cc | 2022-11-25 14:34 | CURRENT | 1 | 0
| RO | 2158 | In Delete NS operation, If VDUs are deleted externally OR VIM is not reachable still osm deletes the ns without any exception or logging. | v12.0 | CONFIRMED | rahul.k4@tataelxsi.co.in | gulsum.atici@canonical.com | 2022-09-07 20:36 | CURRENT | 2022-11-28 23:23 | CURRENT | 2022-09-22 20:51 | keywords | 2022-11-29 00:01 | CURRENT | 3 | 0 |  | 1 | 1
| POL | 2170 | Scale out triggered continuously in case max number of instances reached | v12.0 | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-09-19 10:00 | CURRENT | 2022-09-19 10:00 | CURRENT |  | comment | 2022-11-17 16:06 | CURRENT | 1 | 0
| N2VC | 2173 | Juju can't delete the model | v12.0 | OPEN-UNCONFIRMED | p.korchagin@nexign.com |  | 2022-09-30 10:00 | CURRENT | 2022-09-30 10:00 | CURRENT |  | comment | 2022-12-12 17:01 | CURRENT | 1 | 0
| LCM | 2174 | VCA Update is not implemented | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-09-30 14:22 | CURRENT | 2022-09-30 14:22 | CURRENT |  | priority | 2022-11-29 02:01 | CURRENT | 1 | 0
| LCM | 2175 | K8s-Cluster Update is not implemented | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-09-30 14:36 | CURRENT | 2022-09-30 14:36 | CURRENT |  | priority | 2022-11-29 02:01 | CURRENT | 1 | 0
| OSMClient | 2177 | osm repo-update does not work | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-10-03 11:21 | CURRENT | 2022-10-03 11:21 | CURRENT |  | keywords | 2022-12-07 00:01 | CURRENT | 1 | 0
| LCM | 2179 | Unable to deploy the KDU by using the local helm chart | v12.0 | IN_PROGRESS | gulsum.atici@canonical.com |  | 2022-10-09 13:26 | CURRENT | 2022-10-20 01:01 | CURRENT |  | comment | 2022-12-21 | CURRENT | 2 | 0
| LCM | 2182 | Cannot launch day2 operation which requires input parameters | v10.0 | OPEN-UNCONFIRMED | g.scivoletto@nextworks.it |  | 2022-10-18 18:22 | CURRENT | 2022-10-18 18:22 | CURRENT |  | comment | 2022-12-19 | CURRENT | 1 | 0
| LCM | 2183 | If the VNF package name changes while updating VNFD, charm upgrade operation in a running instance fails | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-10-25 16:39 | CURRENT | 2022-10-25 16:39 | CURRENT |  | comment | 2022-12-26 | RECENT | 1 | 0
| OSMClient | 2189 | package-build fails for most packages | Master | OPEN-UNCONFIRMED | guillermo.gomez.external@atos.net |  | 2022-11-11 14:07 | CURRENT | 2022-11-11 14:07 | CURRENT |  | comment | 2022-12-06 22:50 | CURRENT | 1 | 0 | 1
| LCM | 2190 | Healing fails if the VM created on volume | v12.0 | OPEN-UNCONFIRMED | p.korchagin@nexign.com |  | 2022-11-15 09:59 | CURRENT | 2022-11-15 09:59 | CURRENT |  | cc | 2022-11-15 15:14 | CURRENT | 1 | 0