## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| LCM | 1830 | Missing "NsLcmOperationOccurrenceNotification(COMPLETED)" notification [SOL005] | v12.0 | CONFIRMED | rajeswari.kolluri@oracle.com | gcuba@whitestack.com | 2021-12-15 06:08 | CURRENT | 2023-02-09 17:02 | CURRENT | 2023-02-09 17:02 | comment | 2023-02-09 17:08 | CURRENT | 3 | 1 | 2 | 1 | 2
| NG-UI | 2121 | NG-UI uses unmaintained Chokidar version | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-07-20 17:29 | CURRENT | 2022-07-20 17:29 | CURRENT |  | keywords | 2023-05-16 17:40 | RECENT | 1 | 0

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| RO | 1603 | Dummy VIM fails in HA configuration | Master | CONFIRMED | mark.beierl@canonical.com | gulsum.atici@canonical.com | 2021-07-23 16:10 | CURRENT | 2022-06-07 16:53 | CURRENT | 2022-03-15 13:42 | keywords | 2023-02-15 | CURRENT | 3 | 0 | 1 |  | 2
| common | 1822 | Use mongodb client with asyncio support | Master | OPEN-UNCONFIRMED | david.garcia@canonical.com | mark.beierl@canonical.com | 2021-12-10 10:48 | CURRENT | 2021-12-10 10:48 | CURRENT | 2022-02-16 15:48 | comment | 2023-04-04 17:53 | CURRENT | 1 | 0 |  |  | 1
| RO | 1853 | Error trying to choose disk size for a new VDU in AWS | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:12 | CURRENT | 2022-06-06 22:47 | CURRENT | 2022-03-15 13:00 | comment | 2023-04-18 17:43 | CURRENT | 2 | 0 | 1 |  | 2
| RO | 1856 | User cannot define custom virtual-link-profile with IPv4 CIDR for AWS | Master | CONFIRMED | jgfierro@indra.es | gulsum.atici@canonical.com | 2022-01-10 14:17 | CURRENT | 2023-03-06 14:49 | CURRENT | 2022-03-15 12:59 | comment | 2023-04-18 17:21 | CURRENT | 4 | 1 | 1 |  | 2
| LCM | 1921 | Helm EE has security risks | master | IN_PROGRESS | mark.beierl@canonical.com | gcuba@whitestack.com | 2022-03-21 20:13 | CURRENT | 2022-10-14 20:57 | CURRENT | 2022-09-02 09:02 | comment | 2023-05-16 17:45 | RECENT | 4 | 1 |  |  | 1
| LCM | 2144 | Cannot delete an NS if there are pending actions | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-08-18 20:35 | CURRENT | 2022-08-18 20:35 | CURRENT |  | comment | 2023-03-06 | CURRENT | 1 | 0
| LCM | 2161 | The instantiation of a KNF whose NS parameter vimAccountId causes LCM to throw an exception and the instantiation to fail | v12.0 | IN_PROGRESS | escaleira@av.it.pt |  | 2022-09-12 00:58 | CURRENT | 2023-03-07 05:37 | CURRENT |  | bug_status | 2023-03-07 05:37 | CURRENT | 4 | 1
| OSMClient | 2176 | vca-update using ID modifies the name of the VCA on DB | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-09-30 14:47 | CURRENT | 2022-09-30 14:47 | CURRENT |  | keywords | 2023-02-08 | CURRENT | 1 | 0
| DEVOPS | 2223 | Using hostPath volume in mysql might not be a good idea | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2023-02-27 18:33 | CURRENT | 2023-02-27 18:33 | CURRENT |  | comment | 2023-03-03 13:24 | CURRENT | 1 | 0
| N2VC | 2234 | OSM charms fail to be upgraded with Juju 2.9.29 | v12.0 | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com |  | 2023-04-14 18:28 | CURRENT | 2023-04-14 18:28 | CURRENT |  | comment | 2023-04-14 19:39 | CURRENT | 1 | 0
| IM-NBI | 2241 | Updating VNF descriptors does not work properly | v12.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2023-04-28 14:57 | CURRENT | 2023-04-28 14:57 | CURRENT |  | comment | 2023-04-28 14:57 | CURRENT | 1 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| Gerrit | 2015 | Gerrit no longer closing bugs when patch are merged | unspecified | CONFIRMED | silvia.almagia@etsi.org |  | 2022-04-26 16:58 | CURRENT | 2023-03-10 11:13 | CURRENT |  | comment | 2023-03-10 11:13 | CURRENT | 5 | 2
| RO | 2019 | Onos-vpls plugin should delete ONOS hosts when the NS is deleted | Master | CONFIRMED | glavado@whitestack.com |  | 2022-04-28 16:54 | CURRENT | 2022-11-08 16:42 | CURRENT |  | version | 2023-01-24 10:01 | CURRENT | 3 | 1 | 1
| LCM | 2083 | Helm Chart based EE has access to the overall OSM infrastructure | master | CONFIRMED | escaleira@av.it.pt |  | 2022-06-18 13:58 | CURRENT | 2022-11-08 14:32 | CURRENT |  | keywords | 2023-01-10 | CURRENT | 4 | 1
| LCM | 2088 | Remote Code Execution in N2VC/LCM | master | CONFIRMED | escaleira@av.it.pt | gcuba@whitestack.com | 2022-06-21 20:10 | CURRENT | 2023-05-08 23:00 | RECENT | 2022-08-30 16:54 | keywords | 2023-05-16 17:43 | RECENT | 4 | 1 |  | 1 | 1
| RO | 2093 | Healing fails if the VM has a flavour that is not present in OpenStack | Master | CONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-07-01 10:49 | CURRENT | 2023-03-06 14:50 | CURRENT |  | bug_status | 2023-03-06 14:50 | CURRENT | 4 | 1 | 1
| RO | 2109 | RO creates a copy of VIM details in VDUR section instead of updating existing VIM details in VIM info | Master | CONFIRMED | deepika.e@tataelxsi.co.in |  | 2022-07-08 14:56 | CURRENT | 2023-03-06 14:50 | CURRENT |  | everconfirmed | 2023-03-06 14:50 | CURRENT | 2 | 0 | 1
| RO | 2158 | In Delete NS operation, If VDUs are deleted externally OR VIM is not reachable still osm deletes the ns without any exception or logging. | Master | CONFIRMED | rahul.k4@tataelxsi.co.in | gulsum.atici@canonical.com | 2022-09-07 20:36 | CURRENT | 2023-03-06 14:43 | CURRENT | 2022-09-22 20:51 | comment | 2023-05-17 21:08 | RECENT | 5 | 1 | 1 | 1 | 1
| LCM | 2164 | Upgrade of a CNF does not work when adding a charm not present in original CNF package | v12.0 | CONFIRMED | daguilarh@indra.es |  | 2022-09-14 12:30 | CURRENT | 2023-01-31 00:39 | CURRENT |  | bug_status | 2023-01-31 00:39 | CURRENT | 5 | 1
| LCM | 2167 | Upgrade of CNF does not work when the charm to be updated is a KDU/VDU charm | v12.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | gulsum.atici@canonical.com | 2022-09-15 12:23 | CURRENT | 2023-01-31 15:55 | CURRENT | 2022-09-15 12:32 | keywords | 2023-01-31 15:55 | CURRENT | 3 | 1 |  |  | 1
| LCM | 2168 | Upgrade of charms for NF does not work when the charm is a binary | v12.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | gulsum.atici@canonical.com | 2022-09-15 12:31 | CURRENT | 2023-01-31 15:55 | CURRENT | 2022-09-15 12:32 | keywords | 2023-01-31 15:55 | CURRENT | 3 | 1 |  |  | 1
| POL | 2170 | Scale out triggered continuously in case max number of instances reached | v12.0 | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-09-19 10:00 | CURRENT | 2022-09-19 10:00 | CURRENT |  | keywords | 2023-02-04 | CURRENT | 1 | 0
| OSMClient | 2177 | osm repo-update does not work | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-10-03 11:21 | CURRENT | 2022-10-03 11:21 | CURRENT |  | comment | 2023-02-07 | CURRENT | 1 | 0
| OSMClient | 2189 | package-build fails for most packages | Master | OPEN-UNCONFIRMED | guillermo.gomez.external@atos.net |  | 2022-11-11 14:07 | CURRENT | 2022-11-11 14:07 | CURRENT |  | comment | 2023-02-06 | CURRENT | 1 | 0 | 1
| LCM | 2190 | Healing fails if the VM created on volume | v12.0 | OPEN-UNCONFIRMED | p.korchagin@nexign.com |  | 2022-11-15 09:59 | CURRENT | 2022-11-15 09:59 | CURRENT |  | keywords | 2023-01-16 08:31 | CURRENT | 1 | 0
| RO | 2195 | Healing operation fails if the VM to be healed includes cloud-init | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-11-18 19:43 | CURRENT | 2022-11-18 19:43 | CURRENT |  | comment | 2023-05-15 14:29 | RECENT | 1 | 0
| RO | 2200 | VDU scale operation fails if the specific flavor id is not found in Openstack VIM | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-12-07 17:31 | CURRENT | 2022-12-07 17:31 | CURRENT |  | comment | 2023-02-07 | CURRENT | 1 | 0
| IM-NBI | 2201 | VDU volume instantiation parameters have inconsistency with VNFD | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-12-09 16:23 | CURRENT | 2022-12-09 16:23 | CURRENT |  | comment | 2023-02-09 | CURRENT | 1 | 0
| DEVOPS | 2205 | Prometheus-config-sidecar is not available in charmed-osm | v12.0 | OPEN-UNCONFIRMED | sintechs@gmail.com |  | 2022-12-13 14:06 | CURRENT | 2022-12-13 14:06 | CURRENT |  | comment | 2023-02-13 | CURRENT | 1 | 0
| LCM | 2206 | Error in Scaling of NS launched with Mac IP | v12.0 | OPEN-UNCONFIRMED | pooja.r@tataelxsi.co.in |  | 2022-12-16 12:54 | CURRENT | 2022-12-16 12:54 | CURRENT |  | comment | 2023-02-16 | CURRENT | 1 | 0 |  | 1
| N2VC | 2212 | Error deploying remote URL bundles | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2023-01-23 14:04 | CURRENT | 2023-01-23 14:04 | CURRENT |  | comment | 2023-03-06 19:12 | CURRENT | 1 | 0
| LCM | 2214 | If the VNF package name changes while updating VNFD, charm upgrade operation in a running instance fails | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2023-01-25 15:11 | CURRENT | 2023-01-25 15:11 | CURRENT |  | comment | 2023-03-07 05:30 | CURRENT | 1 | 0
| MON | 2215 | Alarms do not include all Prometheus labels of custom metrics created in run-time | Master | OPEN-UNCONFIRMED | dagomes@av.it.pt |  | 2023-02-10 18:28 | CURRENT | 2023-02-10 18:28 | CURRENT |  | comment | 2023-02-13 13:26 | CURRENT | 1 | 0
| NG-UI | 2219 | NG-UI remains stuck when showing a VIM created from the CLI | Master | OPEN-UNCONFIRMED | dario.faccin@canonical.com |  | 2023-02-22 17:41 | CURRENT | 2023-02-22 17:41 | CURRENT |  | comment | 2023-02-22 17:41 | CURRENT | 1 | 0
| DEVOPS | 2221 | Unit tests for Charms are not being run by Jenkins | v13.0 | OPEN-UNCONFIRMED | daniel.arndt@canonical.com |  | 2023-02-27 15:31 | CURRENT | 2023-02-27 15:31 | CURRENT |  | comment | 2023-02-27 15:31 | CURRENT | 1 | 0
| DEVOPS | 2222 | Charms should not directly invoke event handlers | v13.0 | OPEN-UNCONFIRMED | daniel.arndt@canonical.com |  | 2023-02-27 15:53 | CURRENT | 2023-02-27 15:53 | CURRENT |  | comment | 2023-02-27 15:53 | CURRENT | 1 | 0
| DEVOPS | 2224 | LXD preseed.conf is no longer working with LXD v5.0 | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2023-03-01 15:12 | CURRENT | 2023-03-01 15:12 | CURRENT |  | comment | 2023-03-01 15:12 | CURRENT | 1 | 0
| NG-UI | 2225 | Registration of K8s cluster fails through the GUI | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com | gerardo.garciadeblas@telefonica.com | 2023-03-15 17:43 | CURRENT | 2023-03-15 17:43 | CURRENT | 2023-03-15 17:44 | blocked | 2023-03-15 17:54 | CURRENT | 1 | 0 |  |  | 1
| NG-UI | 2226 | Registration of K8s cluster fails through the GUI | v13.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-03-15 17:47 | CURRENT | 2023-03-15 17:47 | CURRENT |  | dependson | 2023-03-15 17:54 | CURRENT | 1 | 0
| NG-UI | 2227 | Registration of K8s cluster fails through the GUI | v12.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-03-15 17:54 | CURRENT | 2023-03-15 17:54 | CURRENT |  | comment | 2023-03-15 17:54 | CURRENT | 1 | 0