## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| Documentation / Wiki | 2252 | Feature 10911 Vertical scaling of VM instances from OSM needs to be documented | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-01 14:07 | CURRENT | 2023-06-01 14:07 | CURRENT | 2023-06-21 13:03 | short_desc | 2023-06-22 15:06 | CURRENT | 1 | 0 |  |  | 1
| Robot-tests | 2253 | Feature 10911 Vertical scaling of VM instances from OSM requires robot test | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-01 14:10 | CURRENT | 2023-06-01 14:10 | CURRENT | 2023-06-21 13:02 | assigned_to | 2023-06-21 13:02 | CURRENT | 1 | 0 |  |  | 1

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| RO | 1603 | Dummy VIM fails in HA configuration | Master | CONFIRMED | mark.beierl@canonical.com | gulsum.atici@canonical.com | 2021-07-23 16:10 | CURRENT | 2022-06-07 16:53 | CURRENT | 2022-03-15 13:42 | keywords | 2023-02-15 | CURRENT | 3 | 0 | 1 |  | 2
| LCM | 1830 | Missing "NsLcmOperationOccurrenceNotification(COMPLETED)" notification [SOL005] | Master | IN_PROGRESS | rajeswari.kolluri@oracle.com | srojas@whitestack.com | 2021-12-15 06:08 | CURRENT | 2023-07-19 19:05 | CURRENT | 2023-07-19 19:05 | assigned_to | 2023-07-19 19:05 | CURRENT | 4 | 1 | 3 | 1 | 3
| RO | 2019 | Onos-vpls plugin should delete ONOS hosts when the NS is deleted | Master | CONFIRMED | glavado@whitestack.com |  | 2022-04-28 16:54 | CURRENT | 2022-11-08 16:42 | CURRENT |  | version | 2023-01-24 10:01 | CURRENT | 3 | 1 | 1
| RO | 2093 | Healing fails if the VM has a flavour that is not present in OpenStack | Master | CONFIRMED | priyadarshini@tataelxsi.co.in |  | 2022-07-01 10:49 | CURRENT | 2023-03-06 14:50 | CURRENT |  | comment | 2023-07-19 17:20 | CURRENT | 4 | 1 | 1
| OSMClient | 2176 | vca-update using ID modifies the name of the VCA on DB | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-09-30 14:47 | CURRENT | 2022-09-30 14:47 | CURRENT |  | keywords | 2023-02-08 | CURRENT | 1 | 0
| OSMClient | 2177 | osm repo-update does not work | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com |  | 2022-10-03 11:21 | CURRENT | 2022-10-03 11:21 | CURRENT |  | comment | 2023-02-07 | CURRENT | 1 | 0
| NG-UI | 2219 | NG-UI remains stuck when showing a VIM created from the CLI | Master | OPEN-UNCONFIRMED | dario.faccin@canonical.com |  | 2023-02-22 17:41 | CURRENT | 2023-02-22 17:41 | CURRENT |  | comment | 2023-02-22 17:41 | CURRENT | 1 | 0
| DEVOPS | 2223 | Using hostPath volume in mysql might not be a good idea | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2023-02-27 18:33 | CURRENT | 2023-02-27 18:33 | CURRENT |  | comment | 2023-03-03 13:24 | CURRENT | 1 | 0
| IM-NBI | 2241 | Updating VNF descriptors does not work properly | v12.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2023-04-28 14:57 | CURRENT | 2023-04-28 14:57 | CURRENT |  | comment | 2023-04-28 14:57 | CURRENT | 1 | 0
| RO | 2270 | Feature (Start, Stop, Rebuild) The update type shows as completed before VM status is changed in OpenStack of that VM | v14.0 | OPEN-UNCONFIRMED | rahul.k4@tataelxsi.co.in | rahul.k4@tataelxsi.co.in | 2023-07-14 06:09 | CURRENT | 2023-07-14 06:09 | CURRENT | 2023-07-19 17:08 | version | 2023-08-04 11:07 | RECENT | 1 | 0 | 1 |  | 1

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| Bugzilla | 1683 | When a bug is reported or updated, Bugzilla moves to the next bug | unspecified | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2021-10-05 11:50 | CURRENT | 2023-06-14 13:12 | CURRENT |  | comment | 2023-06-14 13:12 | CURRENT | 3 | 1
| Gerrit | 2015 | Gerrit no longer closing bugs when patch are merged | unspecified | CONFIRMED | silvia.almagia@etsi.org |  | 2022-04-26 16:58 | CURRENT | 2023-03-10 11:13 | CURRENT |  | comment | 2023-06-14 14:52 | CURRENT | 5 | 2
| LCM | 2088 | Remote Code Execution in N2VC/LCM | master | CONFIRMED | escaleira@av.it.pt | gcuba@whitestack.com | 2022-06-21 20:10 | CURRENT | 2023-05-08 23:00 | CURRENT | 2022-08-30 16:54 | comment | 2023-06-01 18:04 | CURRENT | 4 | 1 |  | 1 | 1
| LCM | 2144 | Cannot delete an NS if there are pending actions | Master | OPEN-UNCONFIRMED | mark.beierl@canonical.com |  | 2022-08-18 20:35 | CURRENT | 2022-08-18 20:35 | CURRENT |  | comment | 2023-03-06 | CURRENT | 1 | 0
| LCM | 2164 | Upgrade of a CNF does not work when adding a charm not present in original CNF package | v12.0 | CONFIRMED | daguilarh@indra.es |  | 2022-09-14 12:30 | CURRENT | 2023-01-31 00:39 | CURRENT |  | bug_status | 2023-01-31 00:39 | CURRENT | 5 | 1
| RO | 2195 | Healing operation fails if the VM to be healed includes cloud-init | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-11-18 19:43 | CURRENT | 2022-11-18 19:43 | CURRENT |  | comment | 2023-05-15 14:29 | CURRENT | 1 | 0
| RO | 2200 | VDU scale operation fails if the specific flavor id is not found in Openstack VIM | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-12-07 17:31 | CURRENT | 2022-12-07 17:31 | CURRENT |  | comment | 2023-02-07 | CURRENT | 1 | 0
| IM-NBI | 2201 | VDU volume instantiation parameters have inconsistency with VNFD | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2022-12-09 16:23 | CURRENT | 2022-12-09 16:23 | CURRENT |  | comment | 2023-02-09 | CURRENT | 1 | 0
| DEVOPS | 2205 | Prometheus-config-sidecar is not available in charmed-osm | v12.0 | OPEN-UNCONFIRMED | sintechs@gmail.com |  | 2022-12-13 14:06 | CURRENT | 2022-12-13 14:06 | CURRENT |  | comment | 2023-02-13 | CURRENT | 1 | 0
| LCM | 2214 | If the VNF package name changes while updating VNFD, charm upgrade operation in a running instance fails | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2023-01-25 15:11 | CURRENT | 2023-01-25 15:11 | CURRENT |  | comment | 2023-03-07 05:30 | CURRENT | 1 | 0
| MON | 2215 | Alarms do not include all Prometheus labels of custom metrics created in run-time | Master | OPEN-UNCONFIRMED | dagomes@av.it.pt |  | 2023-02-10 18:28 | CURRENT | 2023-02-10 18:28 | CURRENT |  | comment | 2023-02-13 13:26 | CURRENT | 1 | 0
| DEVOPS | 2221 | Unit tests for Charms are not being run by Jenkins | v13.0 | OPEN-UNCONFIRMED | daniel.arndt@canonical.com |  | 2023-02-27 15:31 | CURRENT | 2023-02-27 15:31 | CURRENT |  | comment | 2023-02-27 15:31 | CURRENT | 1 | 0
| DEVOPS | 2222 | Charms should not directly invoke event handlers | v13.0 | OPEN-UNCONFIRMED | daniel.arndt@canonical.com |  | 2023-02-27 15:53 | CURRENT | 2023-02-27 15:53 | CURRENT |  | comment | 2023-02-27 15:53 | CURRENT | 1 | 0
| NG-UI | 2225 | Registration of K8s cluster fails through the GUI | Master | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com | ramerama@tataelxsi.co.in | 2023-03-15 17:43 | CURRENT | 2023-03-15 17:43 | CURRENT | 2023-06-21 13:05 | assigned_to | 2023-06-21 13:05 | CURRENT | 1 | 0 |  |  | 2
| NG-UI | 2226 | Registration of K8s cluster fails through the GUI | v13.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-03-15 17:47 | CURRENT | 2023-03-15 17:47 | CURRENT |  | dependson | 2023-03-15 17:54 | CURRENT | 1 | 0
| NG-UI | 2227 | Registration of K8s cluster fails through the GUI | v12.0 | OPEN-UNCONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-03-15 17:54 | CURRENT | 2023-03-15 17:54 | CURRENT |  | comment | 2023-03-15 17:54 | CURRENT | 1 | 0
| IM-NBI | 2229 | Can not set fixed Ip address for VDU through VNFD or instantiation params | v13.0 | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2023-03-28 16:49 | CURRENT | 2023-03-28 16:49 | CURRENT |  | short_desc | 2023-03-30 11:30 | CURRENT | 1 | 0
| LCM | 2230 | Exception when an instantiating NS with two VNFs to be launched in two different VIMs without a WIM connecting them | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2023-03-28 19:37 | CURRENT | 2023-03-28 19:37 | CURRENT |  | cc | 2023-03-28 19:37 | CURRENT | 1 | 0
| NG-UI | 2232 | k8scluster can't be added with deployment methods | Master | OPEN-UNCONFIRMED | gcuba@whitestack.com |  | 2023-04-04 21:32 | CURRENT | 2023-04-04 21:32 | CURRENT |  | comment | 2023-04-04 21:32 | CURRENT | 1 | 0
| RO | 2233 | compute node information missing in vnfrs record under interfaces | Master | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2023-04-13 10:01 | CURRENT | 2023-04-13 10:01 | CURRENT |  | cc | 2023-04-13 10:03 | CURRENT | 1 | 0
| RO | 2235 | Error launching NS when using multiple VIMs with distinct network names | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2023-04-18 14:33 | CURRENT | 2023-04-18 14:33 | CURRENT |  | comment | 2023-06-11 19:42 | CURRENT | 1 | 0
| MON | 2238 | Error collecting metrics from VIO | v12.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2023-04-21 14:36 | CURRENT | 2023-04-21 14:36 | CURRENT |  | comment | 2023-04-21 14:36 | CURRENT | 1 | 0
| OSMClient | 2240 | VNF packages are listed with "id" but retrieved with "product-name" instead of "id" | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com |  | 2023-04-24 16:50 | CURRENT | 2023-04-24 16:50 | CURRENT |  | comment | 2023-04-24 16:53 | CURRENT | 1 | 0
| N2VC | 2242 | Kafka-k8s and Zookeeper-k8s are not deployed properly in Charmed OSM | v12.0 | OPEN-UNCONFIRMED | guillermo.calvino@canonical.com |  | 2023-05-08 10:19 | CURRENT | 2023-05-08 10:19 | CURRENT |  | version | 2023-05-12 12:46 | CURRENT | 1 | 0 | 1
| IM-NBI | 2243 | Vim Update Tenant issue | v12.0 | OPEN-UNCONFIRMED | haritha.e@tataelxsi.co.in |  | 2023-05-11 09:09 | CURRENT | 2023-05-11 09:09 | CURRENT |  | comment | 2023-05-11 09:09 | CURRENT | 1 | 0
| IM-NBI | 2245 | Timeout error when getting all users | v12.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2023-05-12 15:03 | CURRENT | 2023-05-12 15:03 | CURRENT |  | comment | 2023-07-07 15:44 | CURRENT | 1 | 0
| OSMClient | 2251 | Feature 10911 Vertical scaling of VM instances from OSM needs to be supported by osmclient | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-01 14:01 | CURRENT | 2023-06-01 14:01 | CURRENT | 2023-06-21 13:03 | assigned_to | 2023-06-21 13:03 | CURRENT | 1 | 0 |  |  | 1
| RO | 2255 | VNFr and NSr does not reflect reality after vertical scaling | Master | OPEN-UNCONFIRMED | patricia.reinoso@canonical.com | ramerama@tataelxsi.co.in | 2023-06-13 18:01 | CURRENT | 2023-06-13 18:01 | CURRENT | 2023-06-21 13:02 | assigned_to | 2023-06-21 13:02 | CURRENT | 1 | 0 |  |  | 1
| OSMClient | 2259 | osm repo-index fails with NS packages | v13.0 | OPEN-UNCONFIRMED | ryan.mccloskey@waltoninstitute.ie |  | 2023-06-15 17:15 | CURRENT | 2023-06-15 17:15 | CURRENT |  | comment | 2023-06-15 17:15 | CURRENT | 1 | 0
| OSMClient | 2260 | osm nfpkg-repo-show fails for valid packages | v13.0 | OPEN-UNCONFIRMED | ryan.mccloskey@waltoninstitute.ie |  | 2023-06-15 17:19 | CURRENT | 2023-06-15 17:19 | CURRENT |  | comment | 2023-06-15 17:19 | CURRENT | 1 | 0
| Documentation / Wiki | 2261 | Migrate operation needs to be documented by explaining all the preconditions | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-19 16:32 | CURRENT | 2023-06-19 16:32 | CURRENT | 2023-06-21 13:02 | assigned_to | 2023-06-21 13:02 | CURRENT | 1 | 0 |  |  | 1
| Robot-tests | 2263 | Create robot tests for VM rebuild, start, stop operations | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-20 10:22 | CURRENT | 2023-06-20 10:22 | CURRENT | 2023-06-21 13:00 | assigned_to | 2023-06-21 13:00 | CURRENT | 1 | 0 |  |  | 1
| Robot-tests | 2264 | Create robot tests for vertical scale operation | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-20 10:23 | CURRENT | 2023-06-20 10:23 | CURRENT | 2023-06-21 13:00 | assigned_to | 2023-06-21 13:00 | CURRENT | 1 | 0 |  |  | 1
| Robot-tests | 2265 | Create robot tests for migrate operation | Master | OPEN-UNCONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-20 10:25 | CURRENT | 2023-06-20 10:25 | CURRENT | 2023-06-21 13:00 | assigned_to | 2023-06-21 13:00 | CURRENT | 1 | 0 |  |  | 1