## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| LCM | 2355 | In VNFRS record, IP address is not updated after performing Scale Out first and a Scale In operation | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-03-25 04:53 | CURRENT | 2024-03-25 04:53 | CURRENT |  | comment | 2024-05-26 00:01 | RECENT | 1 | 0

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| RO | 2233 | compute node information missing in vnfrs record under interfaces | Master | OPEN-UNCONFIRMED | priyadarshini@tataelxsi.co.in |  | 2023-04-13 10:01 | CURRENT | 2023-04-13 10:01 | CURRENT |  | comment | 2024-05-12 | RECENT | 1 | 0
| RO | 2235 | Error launching NS when using multiple VIMs with distinct network names | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2023-04-18 14:33 | CURRENT | 2023-04-18 14:33 | CURRENT |  | comment | 2024-05-12 | RECENT | 1 | 0
| IM-NBI | 2241 | Updating VNF descriptors does not work properly | v12.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2023-04-28 14:57 | CURRENT | 2023-04-28 14:57 | CURRENT |  | comment | 2024-05-12 | RECENT | 1 | 0
| RO | 2270 | Feature (Start, Stop, Rebuild) The update type shows as completed before VM status is changed in OpenStack of that VM | Master | CONFIRMED | rahul.k4@tataelxsi.co.in | rahul.k4@tataelxsi.co.in | 2023-07-14 06:09 | CURRENT | 2024-05-21 17:24 | RECENT | 2023-07-19 17:08 | version | 2024-05-27 09:31 | RECENT | 3 | 1 | 2 |  | 1
| OSMClient | 2274 | Cannot perform migration | Master | CONFIRMED | mark.beierl@canonical.com | deepika.e@tataelxsi.co.in | 2023-07-20 15:08 | CURRENT | 2024-05-07 17:51 | CURRENT | 2023-07-20 15:09 | bug_status | 2024-05-07 17:51 | CURRENT | 3 | 1 |  |  | 1
| RO | 2303 | NS instance name getting truncated in OpenStack | v14.0 | CONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2023-11-03 10:26 | CURRENT | 2024-05-21 17:21 | RECENT |  | bug_status | 2024-05-21 17:21 | RECENT | 3 | 1
| RO | 2306 | Monitoring task in RO defined in RO/monitoring.py is replacing the dual-stcak [IPV4, IPV6] with IPV4 in Vnfrs collection. | v14.0 | CONFIRMED | rahul.k4@tataelxsi.co.in |  | 2023-11-06 21:22 | CURRENT | 2024-05-21 17:19 | RECENT |  | comment | 2024-05-27 09:27 | RECENT | 3 | 1
| IM-NBI | 2307 | Invalid references of vdu-id, monitoring-param, storage and compute desc | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2023-11-08 07:03 | CURRENT | 2023-11-08 07:03 | CURRENT |  | comment | 2024-05-23 17:06 | RECENT | 1 | 0
| IM-NBI | 2308 | Able to unlock the User when the user is not locked. | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2023-11-08 11:55 | CURRENT | 2023-11-08 11:55 | CURRENT |  | keywords | 2024-05-10 | RECENT | 1 | 0
| IM-NBI | 2312 | Manual healing is getting triggered, when healed with invalid VDU-Id through CLI. | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2023-11-10 07:49 | CURRENT | 2023-11-10 07:49 | CURRENT |  | comment | 2024-05-20 | RECENT | 1 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| LCM | 2164 | Upgrade of a CNF does not work when adding a charm not present in original CNF package | v12.0 | CONFIRMED | daguilarh@indra.es |  | 2022-09-14 12:30 | CURRENT | 2023-01-31 00:39 | CURRENT |  | keywords | 2024-04-05 | CURRENT | 5 | 1
| LCM | 2230 | Exception when an instantiating NS with two VNFs to be launched in two different VIMs without a WIM connecting them | Master | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2023-03-28 19:37 | CURRENT | 2023-03-28 19:37 | CURRENT |  | comment | 2024-05-12 | RECENT | 1 | 0
| OSMClient | 2243 | Vim Update Tenant issue | v12.0 | CONFIRMED | haritha.e@tataelxsi.co.in |  | 2023-05-11 09:09 | CURRENT | 2024-03-11 17:29 | CURRENT |  | comment | 2024-04-02 17:30 | CURRENT | 2 | 0 |  | 1
| IM-NBI | 2245 | Timeout error when getting all users | v12.0 | OPEN-UNCONFIRMED | e.dah.tid@telefonica.com |  | 2023-05-12 15:03 | CURRENT | 2023-05-12 15:03 | CURRENT |  | comment | 2024-04-02 17:35 | CURRENT | 1 | 0
| Robot-tests | 2263 | Create robot tests for VM rebuild, start, stop operations | Master | CONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-20 10:22 | CURRENT | 2024-05-07 17:30 | CURRENT | 2023-06-21 13:00 | bug_status | 2024-05-07 17:30 | CURRENT | 3 | 1 |  |  | 1
| Robot-tests | 2265 | Create robot tests for migrate operation | Master | CONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-20 10:25 | CURRENT | 2024-05-07 17:31 | CURRENT | 2023-06-21 13:00 | keywords | 2024-05-07 17:31 | CURRENT | 3 | 1 |  |  | 1
| RO | 2286 | Invalid VDU in VNFR if Scale Out is fail | v12.0 | UNCONFIRMED | p.korchagin@nexign.com |  | 2023-08-30 13:57 | CURRENT | 2024-04-10 08:43 | CURRENT |  | bug_status | 2024-04-10 08:43 | CURRENT | 3 | 1
| MON | 2305 | Automated scaling of Vnf is not happening through metrics collected by feature Service KPI of VNF using exporter endpoint. | v14.0 | CONFIRMED | rahul.k4@tataelxsi.co.in |  | 2023-11-06 21:11 | CURRENT | 2024-05-07 17:39 | CURRENT |  | comment | 2024-05-07 17:39 | CURRENT | 3 | 1 |  | 1
| RO | 2310 | NS Termination/Update failing after Vertical-Scaling/Migration/Operate-VNF | v14.0 | CONFIRMED | deepika.e@tataelxsi.co.in |  | 2023-11-09 09:30 | CURRENT | 2024-05-21 17:18 | RECENT |  | keywords | 2024-05-21 17:18 | RECENT | 3 | 1
| IM-NBI | 2313 | Development of User Management environmental variable | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2023-11-14 08:13 | CURRENT | 2023-11-14 08:13 | CURRENT |  | keywords | 2024-05-24 | RECENT | 1 | 0
| IM-NBI | 2314 | Static IPv4 and Dual Stack IP not retained during NS Update (Change VNF Package) | v14.0 | OPEN-UNCONFIRMED | deepika.e@tataelxsi.co.in |  | 2023-11-14 08:22 | CURRENT | 2023-11-14 08:22 | CURRENT |  | keywords | 2024-05-08 | RECENT | 1 | 0
| RO | 2316 | Unable to do vertical scaling when VM is in Shutdown state | v14.0 | CONFIRMED | deepika.e@tataelxsi.co.in |  | 2023-11-14 17:49 | CURRENT | 2024-05-21 17:15 | RECENT |  | resolution | 2024-05-21 17:15 | RECENT | 3 | 1
| IM-NBI | 2322 | OSM does not allow KNF with helm charts using REPO/CHART:VERSION format | Master | CONFIRMED | gcuba@whitestack.com |  | 2023-12-06 06:33 | CURRENT | 2024-04-16 16:50 | CURRENT |  | comment | 2024-05-20 15:58 | RECENT | 3 | 1
| Robot-tests | 2330 | Robot testsuite lcmop_01 fails in daily job when basic_27 testuite leaves NS and NF packages | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com | gerardo.garciadeblas@telefonica.com | 2023-12-20 14:23 | CURRENT | 2024-05-07 09:43 | CURRENT | 2023-12-20 14:23 | keywords | 2024-05-07 09:43 | CURRENT | 3 | 1 |  |  | 1
| Robot-tests | 2331 | Robot testsuite lcmop_01 fails in daily job when basic_27 testuite leaves NS and NF packages | v15.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | gerardo.garciadeblas@telefonica.com | 2023-12-20 14:23 | CURRENT | 2024-05-07 09:44 | CURRENT | 2023-12-20 14:24 | keywords | 2024-05-07 09:44 | CURRENT | 3 | 1 |  |  | 1
| Robot-tests | 2332 | Robot testsuite heal_02 fails in a step when connecting to a manually healed VNF without charms | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-12-20 15:09 | CURRENT | 2024-05-07 09:43 | CURRENT |  | bug_status | 2024-05-07 09:43 | CURRENT | 3 | 1
| Robot-tests | 2333 | Robot testsuite heal_02 fails in a step when connecting to a manually healed VNF without charms | v15.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-12-20 15:10 | CURRENT | 2024-05-07 09:44 | CURRENT |  | resolution | 2024-05-07 09:44 | CURRENT | 3 | 1
| Robot-tests | 2334 | Robot testsuite heal_03 fails when checking if cloudinit worked in a manually healed VNF without charms | Master | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-12-20 17:07 | CURRENT | 2024-05-07 09:45 | CURRENT |  | bug_status | 2024-05-07 09:45 | CURRENT | 3 | 1
| Robot-tests | 2335 | Robot testsuite heal_03 fails when checking if cloudinit worked in a manually healed VNF without charms | v15.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com |  | 2023-12-20 17:07 | CURRENT | 2024-05-07 09:54 | CURRENT |  | resolution | 2024-05-07 09:54 | CURRENT | 3 | 1
| NG-SA | 2337 | Grafana dashboards do not work when NG-SA is enabled | v14.0 | UNCONFIRMED | rzamre@indracompany.com |  | 2024-01-30 14:58 | CURRENT | 2024-05-14 12:51 | RECENT |  | comment | 2024-05-14 13:29 | RECENT | 3 | 1
| DEVOPS | 2338 | OSM installation fails because apt.kubernetes.io was deprecated | v15.0 | CONFIRMED | escaleira@av.it.pt |  | 2024-03-04 17:09 | CURRENT | 2024-03-06 12:02 | CURRENT |  | comment | 2024-05-14 | RECENT | 2 | 0
| RO | 2341 | Invalid vim updation shows Enabled status | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-07 11:14 | CURRENT | 2024-03-07 11:14 | CURRENT |  | comment | 2024-05-08 | RECENT | 1 | 0
| RO | 2342 | Invalid error message while trying to start a VM | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-07 17:03 | CURRENT | 2024-03-07 17:03 | CURRENT |  | comment | 2024-05-16 | RECENT | 1 | 0
| OSMClient | 2343 | After updating the vim account Updated Message is not displaying | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-08 07:11 | CURRENT | 2024-03-08 07:11 | CURRENT |  | comment | 2024-05-09 | RECENT | 1 | 0
| RO | 2345 | NS instantiation is getting failed while trying to launch a NS with detached port | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-10 14:55 | CURRENT | 2024-03-10 14:55 | CURRENT |  | comment | 2024-05-11 | RECENT | 1 | 0
| RO | 2346 | Invalid Vim-Flavor-Id is found in OpenStack VIM after healing operation | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-10 16:43 | CURRENT | 2024-03-10 16:43 | CURRENT |  | comment | 2024-05-11 | RECENT | 1 | 0
| RO | 2347 | Facing inconsistencies while launching NS with Affinity/Anti-Affinity policy | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-11 12:19 | CURRENT | 2024-03-11 12:19 | CURRENT |  | comment | 2024-05-12 | RECENT | 1 | 0
| RO | 2349 | VIM status updation in vnfrs and ro_tasks collection in mongodb | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-13 10:11 | CURRENT | 2024-03-13 10:11 | CURRENT |  | comment | 2024-05-14 | RECENT | 1 | 0
| RO | 2350 | NS update failed while using Affinity/Anti-Affinity policy | Master | OPEN-UNCONFIRMED | kayalvizhi.v@tataelxsi.co.in |  | 2024-03-14 17:31 | CURRENT | 2024-03-14 17:31 | CURRENT |  | comment | 2024-05-15 | RECENT | 1 | 0
| IM-NBI | 2351 | Able to Update user role even with project user role | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-18 10:00 | CURRENT | 2024-03-18 10:00 | CURRENT |  | comment | 2024-04-04 09:29 | CURRENT | 1 | 0
| IM-NBI | 2352 | While updating roles existing roles are not getting deleted | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-18 10:53 | CURRENT | 2024-03-18 10:53 | CURRENT |  | keywords | 2024-05-24 | RECENT | 1 | 0
| IM-NBI | 2353 | Unable to update roles for few role permissions | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-19 09:46 | CURRENT | 2024-03-19 09:46 | CURRENT |  | keywords | 2024-05-24 | RECENT | 1 | 0
| IM-NBI | 2356 | Able to update User with same project and role multiple times | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-25 07:32 | CURRENT | 2024-03-25 07:32 | CURRENT |  | comment | 2024-05-26 00:01 | RECENT | 1 | 0
| IM-NBI | 2357 | Facing issue while deleting the Project and Role tagged with the Admin User | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-25 10:20 | CURRENT | 2024-03-25 10:20 | CURRENT |  | comment | 2024-05-26 00:01 | RECENT | 1 | 0
| POL | 2358 | Alarm Number for Alarm notification is getting started from 0 when metric value is increased just after instantiation. | v14.0 | OPEN-UNCONFIRMED | kosinepalli.s@tataelxsi.co.in |  | 2024-03-26 05:51 | CURRENT | 2024-03-26 05:51 | CURRENT |  | comment | 2024-05-09 08:42 | RECENT | 1 | 0