## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 2312 | Manual healing is getting triggered, when healed with invalid VDU-Id through CLI. | v14.0 | CONFIRMED | jegan.s@tataelxsi.co.in |  | 2023-11-10 07:49 | CURRENT | 2024-06-25 16:58 | CURRENT |  | everconfirmed | 2024-06-25 16:58 | CURRENT | 2 | 0
| IM-NBI | 2314 | Static IPv4 and Dual Stack IP not retained during NS Update (Change VNF Package) | v14.0 | CONFIRMED | deepika.e@tataelxsi.co.in |  | 2023-11-14 08:22 | CURRENT | 2024-06-25 16:56 | CURRENT |  | everconfirmed | 2024-06-25 16:56 | CURRENT | 2 | 0

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| RO | 2271 | Instantiation with persistent volume fails when the sw-image-desc does not exist in VIM | Master | CONFIRMED | gcuba@whitestack.com |  | 2023-07-14 07:18 | CURRENT | 2024-06-04 17:20 | CURRENT |  | comment | 2024-06-10 17:36 | CURRENT | 3 | 1
| RO | 2298 | Having multiple replicas of RO can generate conflicts among workers across them. | v14.0 | CONFIRMED | lvega@whitestack.com |  | 2023-10-26 18:25 | CURRENT | 2024-06-04 17:20 | CURRENT |  | comment | 2024-08-05 | RECENT | 3 | 1
| IM-NBI | 2352 | While updating roles existing roles are not getting deleted | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-18 10:53 | CURRENT | 2024-07-16 17:06 | CURRENT |  | comment | 2024-07-16 17:06 | CURRENT | 2 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| LCM | 2164 | Upgrade of a CNF does not work when adding a charm not present in original CNF package | v12.0 | CONFIRMED | daguilarh@indra.es |  | 2022-09-14 12:30 | CURRENT | 2023-01-31 00:39 | CURRENT |  | keywords | 2024-06-11 | CURRENT | 5 | 1
| OSMClient | 2243 | Vim Update Tenant issue | Master | CONFIRMED | haritha.e@tataelxsi.co.in |  | 2023-05-11 09:09 | CURRENT | 2024-03-11 17:29 | CURRENT |  | comment | 2024-06-10 17:31 | CURRENT | 2 | 0 | 1 | 1
| Robot-tests | 2263 | Create robot tests for VM rebuild, start, stop operations | Master | CONFIRMED | gulsum.atici@canonical.com | ramerama@tataelxsi.co.in | 2023-06-20 10:22 | CURRENT | 2024-05-07 17:30 | CURRENT | 2023-06-21 13:00 | comment | 2024-06-10 17:33 | CURRENT | 3 | 1 |  |  | 1
| RO | 2286 | Invalid VDU in VNFR if Scale Out is fail | v12.0 | UNCONFIRMED | p.korchagin@nexign.com |  | 2023-08-30 13:57 | CURRENT | 2024-04-10 08:43 | CURRENT |  | keywords | 2024-06-12 | CURRENT | 3 | 1
| IM-NBI | 2322 | OSM does not allow KNF with helm charts using REPO/CHART:VERSION format | Master | CONFIRMED | gcuba@whitestack.com |  | 2023-12-06 06:33 | CURRENT | 2024-04-16 16:50 | CURRENT |  | comment | 2024-07-21 | RECENT | 3 | 1
| Robot-tests | 2331 | Robot testsuite lcmop_01 fails in daily job when basic_27 testuite leaves NS and NF packages | v15.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | gerardo.garciadeblas@telefonica.com | 2023-12-20 14:23 | CURRENT | 2024-05-07 09:44 | CURRENT | 2023-12-20 14:24 | comment | 2024-07-08 | CURRENT | 3 | 1 |  |  | 1
| NG-SA | 2337 | Grafana dashboards do not work when NG-SA is enabled | v14.0 | CONFIRMED | rzamre@indracompany.com |  | 2024-01-30 14:58 | CURRENT | 2024-06-25 16:55 | CURRENT |  | comment | 2024-07-15 16:16 | CURRENT | 4 | 1
| IM-NBI | 2353 | Unable to update roles for few role permissions | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-19 09:46 | CURRENT | 2024-07-16 16:59 | CURRENT |  | comment | 2024-07-16 16:59 | CURRENT | 2 | 0
| LCM | 2361 | VM is not getting deleted from openstack after Scale In operation. | v14.0 | UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-03-30 16:08 | CURRENT | 2024-07-01 11:11 | CURRENT |  | comment | 2024-07-01 18:49 | CURRENT | 3 | 1
| LCM | 2362 | Operational-status is not getting updated when healing is triggered | v14.0 | IN_PROGRESS | jegan.s@tataelxsi.co.in |  | 2024-03-30 17:07 | CURRENT | 2024-04-16 05:15 | CURRENT |  | comment | 2024-07-30 | RECENT | 2 | 0
| LCM | 2365 | Modified time in vnfrs collection of mongo database is not updated, after healing operation | v14.0 | IN_PROGRESS | jegan.s@tataelxsi.co.in |  | 2024-04-01 13:28 | CURRENT | 2024-05-28 20:48 | CURRENT |  | comment | 2024-06-07 07:16 | CURRENT | 3 | 0
| IM-NBI | 2366 | Static Inactive session timeout for a user | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-04-01 13:38 | CURRENT | 2024-04-01 13:38 | CURRENT |  | comment | 2024-07-01 10:26 | CURRENT | 1 | 0
| LCM | 2368 | Mac address is missing in Additional params section of Vnfrs Collection in Mongodb | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-04-02 06:53 | CURRENT | 2024-04-02 06:53 | CURRENT |  | comment | 2024-07-29 | RECENT | 1 | 0
| LCM | 2369 | Operational Dashboard is not enabled after instantiating charm packages | v14.0 | IN_PROGRESS | adurti.v@tataelxsi.co.in |  | 2024-04-02 11:27 | CURRENT | 2024-05-29 21:54 | CURRENT |  | comment | 2024-07-30 | RECENT | 3 | 0
| RO | 2370 | Healing fails if the corresponding flavor does not exist in VIM | v14.0 | OPEN-UNCONFIRMED | deepika.e@tataelxsi.co.in |  | 2024-05-07 08:41 | CURRENT | 2024-05-07 08:41 | CURRENT |  | comment | 2024-07-08 | CURRENT | 1 | 0
| IM-NBI | 2371 | Able to update sfc nsd descriptor even with invalid references | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-05-07 11:42 | CURRENT | 2024-05-07 11:42 | CURRENT |  | comment | 2024-07-08 | CURRENT | 1 | 0
| IM-NBI | 2372 | Vnf Descriptor is getting updated without giving any value under min and max number of instances | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-05-07 13:05 | CURRENT | 2024-05-07 13:05 | CURRENT |  | comment | 2024-06-21 08:08 | CURRENT | 1 | 0
| OSMClient | 2373 | OSM NS-Show command is not working while using OSMCLIENT | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-05-07 13:23 | CURRENT | 2024-05-07 13:23 | CURRENT |  | comment | 2024-06-20 12:08 | CURRENT | 1 | 0
| OSMClient | 2374 | IP's are not listed properly when using vnf-list command in OSMCLIENT | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-05-07 13:38 | CURRENT | 2024-05-07 13:38 | CURRENT |  | keywords | 2024-07-13 | CURRENT | 1 | 0
| IM-NBI | 2375 | Unable to get notification during NS instantiation using SOL003 APIs | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-05-08 07:18 | CURRENT | 2024-05-08 07:18 | CURRENT |  | comment | 2024-07-09 | CURRENT | 1 | 0
| OSMClient | 2376 | Performing NS-Update through CLI | v14.0 | OPEN-UNCONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-05-16 07:30 | CURRENT | 2024-05-16 07:30 | CURRENT |  | comment | 2024-07-09 17:10 | CURRENT | 1 | 0
| IM-NBI | 2377 | NS-Update operation does not work for KNF | v14.0 | OPEN-UNCONFIRMED | p.korchagin@nexign.com |  | 2024-05-28 11:23 | CURRENT | 2024-05-28 11:23 | CURRENT |  | comment | 2024-07-29 | RECENT | 1 | 0
| IM-NBI | 2378 | max-age and expires are exposed in API cookies | v14.0 | OPEN-UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-06-03 08:52 | CURRENT | 2024-06-03 08:52 | CURRENT |  | comment | 2024-08-04 | RECENT | 1 | 0
| RO | 2379 | RO crashes when VIM is down | Master | OPEN-UNCONFIRMED | deepika.e@tataelxsi.co.in |  | 2024-06-03 11:15 | CURRENT | 2024-06-03 11:15 | CURRENT |  | comment | 2024-07-17 06:13 | RECENT | 1 | 0