## 0. Too old bugs still open
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES

## 1. Open outliers
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 2312 | Manual healing is getting triggered, when healed with invalid VDU-Id through CLI. | v14.0 | CONFIRMED | jegan.s@tataelxsi.co.in |  | 2023-11-10 07:49 | CURRENT | 2024-11-27 04:49 | CURRENT |  | comment | 2024-12-19 16:06 | RECENT | 4 | 1
| IM-NBI | 2314 | Static IPv4 and Dual Stack IP not retained during NS Update (Change VNF Package) | v14.0 | CONFIRMED | deepika.e@tataelxsi.co.in |  | 2023-11-14 08:22 | CURRENT | 2024-06-25 16:56 | CURRENT |  | comment | 2024-12-01 | CURRENT | 2 | 0

## 2. Open beyond q3
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| IM-NBI | 2351 | Able to Update user role even with project user role | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-18 10:00 | CURRENT | 2024-10-24 16:49 | CURRENT |  | comment | 2024-12-23 09:19 | RECENT | 4 | 1
| LCM | 2361 | VM is not getting deleted from openstack after Scale In operation. | v14.0 | IN_PROGRESS | jegan.s@tataelxsi.co.in |  | 2024-03-30 16:08 | CURRENT | 2024-11-26 03:00 | CURRENT |  | bug_status | 2024-11-26 03:00 | CURRENT | 5 | 1
| RO | 2391 | Healing issue for VDU with persistent-storage | Master | OPEN-UNCONFIRMED | dakornev1@mts.ru |  | 2024-10-18 13:59 | CURRENT | 2024-10-18 13:59 | CURRENT |  | comment | 2024-12-19 | RECENT | 1 | 0

## 3. Open beyond 2 months
RECOMMENDATION | MODULE | BUG_ID | BUG_DESCRIPTION | RELEASE | STATE | ISSUER | OWNER | CREATION_TIME | CREATION_AGE | STATE_UPDATE_TIME | STATE_UPDATE_AGE | LAST_ASSIGNMENT_TIME | LAST_EVENT | LAST_EVENT_TIME | LAST_EVENT_AGE | STATE_CHANGES | CHANGES_TO_RESOLVED | RELEASE_CHANGES | MODULE_CHANGES | OWNER_CHANGES
| Robot-tests | 2331 | Robot testsuite lcmop_01 fails in daily job when basic_27 testuite leaves NS and NF packages | v15.0 | CONFIRMED | gerardo.garciadeblas@telefonica.com | gerardo.garciadeblas@telefonica.com | 2023-12-20 14:23 | CURRENT | 2024-08-07 00:08 | CURRENT | 2023-12-20 14:24 | comment | 2024-12-01 | CURRENT | 5 | 2 |  |  | 1
| IM-NBI | 2353 | Unable to update roles for few role permissions | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-19 09:46 | CURRENT | 2024-10-21 11:01 | CURRENT |  | comment | 2024-12-22 | RECENT | 4 | 1
| IM-NBI | 2356 | Able to update User with same project and role multiple times | v14.0 | UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-25 07:32 | CURRENT | 2024-10-21 11:01 | CURRENT |  | comment | 2024-12-13 09:31 | RECENT | 3 | 1
| IM-NBI | 2357 | Facing issue while deleting the Project and Role tagged with the Admin User | v14.0 | UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-03-25 10:20 | CURRENT | 2024-10-21 11:01 | CURRENT |  | comment | 2024-12-24 06:04 | RECENT | 3 | 1
| NG-UI | 2366 | Static Inactive session timeout for a user | v14.0 | CONFIRMED | jegan.s@tataelxsi.co.in | sandhya.j@tataelxsi.co.in | 2024-04-01 13:38 | CURRENT | 2024-09-30 17:56 | CURRENT | 2024-12-03 16:38 | cc | 2024-12-03 16:38 | CURRENT | 2 | 0 |  | 1 | 1
| LCM | 2368 | Mac address is missing in Additional params section of Vnfrs Collection in Mongodb | v14.0 | CONFIRMED | jegan.s@tataelxsi.co.in |  | 2024-04-02 06:53 | CURRENT | 2024-11-25 12:15 | CURRENT |  | comment | 2024-11-26 04:55 | CURRENT | 3 | 1
| LCM | 2369 | Operational Dashboard is not enabled after instantiating charm packages | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-04-02 11:27 | CURRENT | 2024-10-21 11:00 | CURRENT |  | comment | 2024-12-22 | RECENT | 5 | 1
| IM-NBI | 2371 | Able to update sfc nsd descriptor even with invalid references | v14.0 | UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-05-07 11:42 | CURRENT | 2024-10-21 11:02 | CURRENT |  | comment | 2024-12-22 | RECENT | 3 | 1
| IM-NBI | 2372 | Vnf Descriptor is getting updated without giving any value under min and max number of instances | v14.0 | UNCONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-05-07 13:05 | CURRENT | 2024-10-21 11:02 | CURRENT |  | comment | 2024-12-22 | RECENT | 3 | 1
| IM-NBI | 2375 | Unable to get notification during NS instantiation using SOL003 APIs | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-05-08 07:18 | CURRENT | 2024-11-25 12:13 | CURRENT |  | bug_status | 2024-11-25 12:13 | CURRENT | 4 | 1
| IM-NBI | 2378 | max-age and expires are exposed in API cookies | v14.0 | CONFIRMED | adurti.v@tataelxsi.co.in |  | 2024-06-03 08:52 | CURRENT | 2024-11-26 16:41 | CURRENT |  | bug_status | 2024-11-26 16:41 | CURRENT | 4 | 1
| LCM | 2383 | KNFs with metrics are not working properly | v15.0 | OPEN-UNCONFIRMED | escaleira@av.it.pt |  | 2024-10-15 17:53 | CURRENT | 2024-10-15 17:53 | CURRENT |  | comment | 2024-12-16 | RECENT | 1 | 0
| NG-SA | 2384 | ) By stopping Gnocchi services, VM status and VIM status metrics were not collected when OSM is deployed with NGSA | Master | OPEN-UNCONFIRMED | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 10:15 | CURRENT | 2024-10-16 10:15 | CURRENT |  | comment | 2024-11-01 07:47 | CURRENT | 1 | 0 | 1
| NG-SA | 2385 | VIM resource overview feature is not supported when OSM is deployed with NGSA. | Master | OPEN-UNCONFIRMED | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 10:40 | CURRENT | 2024-10-16 10:40 | CURRENT |  | version | 2024-10-28 06:56 | CURRENT | 1 | 0 | 1
| NG-SA | 2386 | Airflow DAGs should not check for VM status if VIM status is down | Master | OPEN-UNCONFIRMED | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 10:41 | CURRENT | 2024-10-16 10:41 | CURRENT |  | version | 2024-10-28 06:56 | CURRENT | 1 | 0 | 1
| LCM | 2387 | Alerts (Policy updates) are not updated when NS update feature is triggered. | Master | IN_PROGRESS | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 10:45 | CURRENT | 2024-11-26 03:01 | CURRENT |  | bug_status | 2024-11-26 03:01 | CURRENT | 2 | 0 | 1
| LCM | 2388 | Healing is not happening for scaled out VM using NGSA. | Master | IN_PROGRESS | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 10:47 | CURRENT | 2024-11-26 01:09 | CURRENT |  | bug_status | 2024-11-26 01:09 | CURRENT | 2 | 0 | 1
| NG-SA | 2389 | Alarm number is not available in the payload when monitoring parameter is more than threshold when OSM deployed with NGSA. | Master | OPEN-UNCONFIRMED | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 11:20 | CURRENT | 2024-10-16 11:20 | CURRENT |  | version | 2024-10-28 06:56 | CURRENT | 1 | 0 | 1
| NG-SA | 2390 | Repeated alarm notification is sent to the URL when threshold value is reached. | Master | OPEN-UNCONFIRMED | kosinepalli.s@tataelxsi.co.in |  | 2024-10-16 11:22 | CURRENT | 2024-10-16 11:22 | CURRENT |  | version | 2024-10-28 06:56 | CURRENT | 1 | 0 | 1